## Meta Data
RBEI_ECN_Billing_Status
Meeting Minutes
#REF!
Document Meta Data:
Project (Number and Name) |  | RBEI_ECN_Billing_Status
Document Approver |  | Xia Sammi
Document Status |  | Draft
Note: Press F9 to update the automatic calculated fields
Note: Version history is updated automatic, when new Meeting is generated.
Version | Author | Date | Change (Why, What)
1 | Sammi | 2020-03-09 | -GE12B SOP+6 billing done -GE13 PP phase renamed as TT2 and delayed till 5/1 and SOP+6 till 10/31 - BYD the 1st phase will be delayed till 5/31 - GAC the 1st phase will be delayed till 7/31
2 | Sammi | 2020-03-23 | - add FE3AH into the list
3 | Sammi | 2020-04-28 | - GE13 TT1 phase billing finished - FE5AB/6AB VP2 phase billing finished
4 | Sammi | 2020-05-21 | - FE6AB TT phase delay, billing plan updated - GAC 1st phase delay till 8/31, billing plan updated - BYD 1st phase delay till 7/31, billing plan updated - DFM confirmed the entering date, project plan updated
5 | Sammi | 2020-06-18 | - Add RBJAC payment plan - Add BJEV payment plan
6 | Sammi | 2020-06-30 | - FE5AB/6AB TT phase billing finished - FE3AH delayed because the customer software releasing one month late
7 | Sammi | 2020-07-08 | - add the FE5AB/6AB_extension project
8 | Sammi | 2020-07-20 | - add the FE5AB/6AB_3rd Party_1 project
9 | Sammi | 2020-08-07 | - FE3AH 1 phase payment done - FE5AB/6AB_3rd Party_1 total payment done - add GAC complex driver
10 | Sammi | 2020-08-27 | - DFM prepayment done
11 | Sammi | 2020-09-26 | - DFM 1st done - FE5AB/6AB_3rd Party_2 total payment done - FE5AB/6AB PP phase done -BYD will delay to Oct
12 | Sammi | 2020-11-11 | - FE5AB/6AB billing complete done, last 10% shift from 2021 to 2020 - FE3AH billing complete done, last 10% shift from 2021 to 2020 - FE5AB/6AB extend billing complete done
13 | Sammi | 2020-12-11 | - GAC 1st payment done
14 | Sammi | 2020-12-17 | -update BJEV billing percentage of each phase according to the contract'
15 | Sammi | 2021-02-22

## Billing Status
| RBEI/ECN Billing Status (W/O. Tax) | [9 empty] | -73782.54
| Project Name | Milestone | Planned Closure Date | Actual Closure Date | Total Amount | Payment Percentage | Amount (RMB) | Invoicing Status | 2019 Forecast | 2020 Forecast | 2021 Forecast | 2022 Forecast | 2023 Forecast | Paid to vendor | Profit CN | Profit CN (Total) | Plan to bill in 2021 | Rest payment in 2021
| CF03_Plan | 31th Mar 2021 | [5 empty] | -GAC_PT and GAC_CDD was blocked by internal credit applying -BJEV was blocked because the deliverables review |  |  | 1911955.6604
| CF03_Actual | [9 empty] | 867924.5283
| CF06_Plan | 30th Jun 2021 | [5 empty] | -BJEV will be reversed in Apr. -RBJAC and RBJAC commercial will happen in advance -BYD was blocked |  |  | 2322830.1887
| CF06_Actual | [9 empty] | 3033842.4528
| CF09_Plan | 30th Sep 2021 | [5 empty] | All planned Milstone was delayed by the acceptence process and contracting |  |  | 1425053.2075
| CF09_Actual | [9 empty] | 0
| CF12_Plan | 31th Dec 2021 | [8 empty] | 1453773.5849
CF12_Actual
| Total_Plan | 31th Dec 2021 | [8 empty] | 7113612.6415
| Total_Actual | [9 empty] | 3901766.9811
GE13 | GE13 | M2 Test Phase | 2019-03-30 | 2019-03-30 | 3394339.6226 | 20% | 678867.9 | Done | 1866886.7 | - | 0 |  |  | -3710855.9528 | -1843969.2528 | -2695119.9891
GE13 |  | M2-2 Test Phase | 2019-09-20 | 2019-08-30 |  | 20% | 678867.9 | Done
GE13 |  | VP2 Test Phase | 2019-11-30 | 2019-11-30 |  | 15% | 509150.9 | Done
GE13 |  | TT1 Test Phase | 2020-01-30 | 2020-02-28 |  | 15% | 509150.9 | Done | - | 1527452.8 | 0 |  |  | -2378603.6589 | -851150.8589
GE13 |  | TT2 Test Phase | 2020-03-31 | 2020-05-31 |  | 20% | 678867.9 | Done
GE13 |  | SOP +6 | 2020-08-31 | 2020-11-30 |  | 10% | 339434 | Done
GE12B | GE12B | VP2 Test Phase | 2019-04-30 | 2019-07-04 | 896226.4151 |  | 358490.57 | Done | 806603.78 | - | 0 |  |  | -914468.9575 | -107865.1775 | -18242.5375
GE12B |  | TT Test Phase | 2019-07-20 | 2019-08-30 |  |  | 448113.21 | Done
GE12B |  | SOP +6 | 2020-02-20 | 2020-02-28 |  |  | 89622.64 | Done | - | 89622.64 |  |  |  | 0 | 89622.64
FE5AB/6AB | FE5AB/6AB | VP1 Test Phase | 2020-01-30 | 2020-01-30 | 2036686.7925 | 20% | 407337.3585 | Done | 0 | 1833018.1132 | 0 |  |  | -944371.5283 | -944371.5283 | -827721.5952
FE5AB/6AB |  | VP2 Test Phase | 2020-03-30 | 2020-03-30 |  | 20% | 407337.3585 | Done | [5 empty] | -2198338.7461 | 116649.9331
FE5AB/6AB |  | TT Test Phase | 2020-05-30 | 2020-06-30 |  | 20% | 407337.3585 | Done
FE5AB/6AB |  | PP Test Phase | 2020-08-30 | 2020-10-31 |  | 30% | 611006.0377 | Done
FE5AB/6AB |  | SOP+6 | 2021-01-30 | 2020-11-04 |  | 10% | 203668.6792 | Done |  | 203668.6792 | 0
FE5AB/6AB_Extension | FE5AB/6AB_Extension |  | 2020-08-30 | 2020-08-30 | 122641.5094 | 100% | 122641.5094 | Done |  | 122641.5094 | 0
FE5AB/6AB_3rd Party_1 | FE5AB/6AB_3rd Party_1 |  | 2020-08-30 | 2020-08-07 | 75471.6981 | 100% | 75471.6981 | Done |  | 75471.6981 | 0 | [9 empty] | -2521319.8784
FE5AB/6AB_3rd Party_2 | FE5AB/6AB_3rd Party_2 |  | 2020-09-30 | 2020-09-30 | 80188.6792 | 100% | 80188.6792 | Done |  | 80188.6792 | 0
UAES | UAES | 1st phase | - | - | 243000 | 50% | 121500 | Done | 243000 | - | - |  |  | 0 | 243000 | 243000
UAES |  | 2nd phase | - | 2019-11-30 |  | 50% | 121500 | Done |  | - | -
BYD | BYD | Prepayment | 2019-10-30 | 2019-10-30 | 1462264.1509 | 30% | 438679.2453 | Done | 438679.2453 |  | 0 |  |  | -180931.816 | 257747.4292 | 908576.0896 |  | 292452.8302
BYD |  | 1st phase | 2020-04-17 | 2020-11-30 |  | 30% | 438679.2453 | Done | - | 438679.2453 | 0 |  |  | -226529.8302 | 212149.4151
BYD |  | 2nd phase | 2020-05-30 | 2021-11-30 |  | 30% | 438679.2453 | Delayed, alternative solution for Variant 3 setup |  | - | 438679.2453
BYD |  | 3rd phase | 2020-11-30 | 2022-04-30 |  | 10% | 146226.4151 | Not yet |  |  |  | 146226.4151 |  |  | 438679.2453
GAC | GAC | Prepayment | 2019-11-30 | 2019-11-30 | 1584905.6604 | 40% | 633962.2642 | Done | 633962.2642 |  | 0 |  |  | 0 | 633962.2642 | 1576064.1509 |  |  |  | 1500000
GAC |  | 1st phase | 2020-04-20 | 2020-11-30 |  | 20% | 316981.1321 | Done | - | 316981.1321 | 0 |  |  | -8841.5094 | 308139.6226 |  |  |  |  | 450000
GAC |  | 2nd phase | 2020-07-10 | 2021-03-30 |  | 30% | 475471.6981 | Done |  |  | 633962.2642 | [7 empty] | 4400000 | 1050000
GAC |  | 3rd phase | 2021-01-10 | 2021-09-30 |  | 10% | 158490.566 | Delayed | [6 empty] | 633962.2642 |  |  |  | 8828826.7925 | 150000
DFM | DFM | Prepayment | 2020-04-30 | 2020-08-15 | 1132075.4717 | 30% | 339622.6415 | Done | - | 1018867.9245 | 0 |  |  | -201219.8113 | 817648.1132 | 817648.1132 |  |  | 1261260.9704
DFM |  | 1st phase | 2020-09-30 | 2020-09-30 |  | 60% | 679245.283 | Done, but risk for payment | [10 empty] | 628571.4286
DFM |  | 2nd phase | 2020-12-31 | 2020-12-31 |  | 10% | 113207.5472 | Canceled, because of the delay |  |  | 0 | [5 empty] | 0 |  |  | CF billing | 2039832.3989
FE3AH | FE3AH | VP Test Phase | 2020-05-15 | 2020-07-30 | 943394.3396 | 40% | 377357.7358 | Done | - | 849054.9057 | 0 |  |  | -1132912.1462 | -283857.2406 | -283857.2406 |  |  |  | shaohaihui | 250000
FE3AH |  | TT&PP Test Phase | 2020-07-30 | 2020-09-30 |  | 50% | 471697.1698 | Done |  |  | 0 | [8 empty] | Audi-2nd phase | 502021.5633
FE3AH |  | SOP+6 | 2021-02-28 | 2020-11-04 |  | 10% | 94339.434 | Done |  | 94339.434 | 0 |  |  |  | 0 |  |  |  |  | Nanjing | 666666.6667 | 214200
RBJAC | RBJAC | FRS D0 | 2020-07-30 | 2020-09-30 | 1930188.6792 | 30% | 579056.6038 | Done | - | 1544150.9434 | 0 |  |  | 0 | 0 | 0 |  |  | 13228826.7925 | Garett | 100000
RBJAC |  | FRS Bugfix | 2020-10-30 | 2020-11-30 |  | 50% | 965094.3396 | Done | [10 empty] | 1889832.3989 | GPE
RBJAC |  | Final Acceptence | 2021-05-30 | 2021-04-30 |  | 20% | 386037.7358 | Done |  |  | 386037.7358 |  |  | 0 | 0
BJEV | BJEV | Prepayment | 2020-09-15 | 2020-12-15 | 1392041.5094 | 15% | 208806.2264 | Done | - | 208806.2264 |  |  |  | 0 | 0 | 0 |  | 1392041.5094
BJEV |  | 1st phase | 2021-01-15 | 2021-05-15 |  | 75% | 1044031.1321 | Done |  |  | 1183235.283 |  |  | 0 | 0
BJEV |  | 2nd phase | 2021-07-15 | 2021-09-15 |  | 10% | 139204.1509 | Not yet | [8 empty] | 139204.1509
GAC_Complex Driver | GAC_Complex Driver | Prepayment | 2020-09-30 | 2021-03-01 | 1962264.1509 | 20% | 392452.8302 | Done | - | - | 1569811.3208 |  |  | 0 | 0 | 0
GAC_Complex Driver |  | 1st phase | 2021-05-01 | 2021-11-30 |  | 60% | 1177358.4906 | Delayed, because offshore delivery blocking | [5 empty] | 0 | 0 |  | 1177358.4906 | 1177358.4906
GAC_Complex Driver |  | 2nd phase | 2021-11-01 | 2022-05-01 |  | 20% | 392452.8302 | Delayed, because offshore delivery blocking |  |  |  | 392452.8302
RBJAC_commercial | RBJAC_commercial | FRS D0 | 2021-04-01 | 2021-04-01 | 1603773.5849 | 20% | 320754.717 | Done | - | - | 1603773.5849 |  |  | 0 | 0 | 0 |  | 1603773.5849
RBJAC_commercial |  | FRS D1& Bugfix | 2021-05-30 | 2021-06-30 |  | 50% | 801886.7925 | Done
RBJAC_commercial |  | Final Acceptence | 2021-12-15 | 2021-06-30 |  | 30% | 481132.0755 | Done | [5 empty] | 0 | 0
FE-6-A3 | FE-6-A3 | VP Test Phase | 2021-08-30 | 12/12/2012 | 1084905.6604 | 30% | 325471.6981 | Delayed, because the whole customer SOP timeline changing | - | 759433.9623 | 325471.6981 | [5 empty] | 325471.6981
FE-6-A3 |  | TT&PP Test Phase | 2021-12-30 | 2022-04-30 |  | 40% | 433962.2642 | Delayed, because the whole customer SOP timeline changing |  |  |  | 650943.3962
FE-6-A3 |  | SOP+6 | 2022-06-30 | 2022-10-30 |  | 20% | 216981.1321 | Not yet
AUDI_PPE&CADA&CAPA | AUDI_PPE&CADA&CAPA | Q1 | 2021-09-30 | 2021-11-30 | 7028301.8868 | 50% | 3514150.9434 | Delayed, because the contracting was blocked |  |  | 7028301.8868 | [5 empty] | 7028301.8868 | 7028301.8868
AUDI_PPE&CADA&CAPA |  | Q2 | 2021-12-30 | 2021-12-30 |  | 50% | 3514150.9434 | Not yet
Baoneng_GX16_EE | Baoneng_GX16_EE | Prepayment | 2021-08-30 | / | 3675471.6981 | 30% | 1102641.5094 | Cancel
Baoneng_GX16_EE |  | 1st phase | 2021-11-30 | / |  | 30% | 1102641.5094 | Cancel
Baoneng_GX16_EE |  | 2nd phase | 2022-02-28 | / |  | 30% | 1102641.5094 | Cancel
Baoneng_GX16_EE |  | 3rd phase | 2022-11-30 | / |  | 10% | 367547.1698 | Cancel
VF11-A2 | VF11-A2 | VP Test Phase | 2022-03-31 | 2022-03-31 | 764150.9434 | 40% | 305660.3774 | Not yet |  |  |  | 687735.8491
VF11-A2 |  | J1 Test Phase | 2022-09-30 | 2022-09-30 |  | 50% | 382075.4717 | Not yet
VF11-A2 |  | SOP+6 | 2023-03-31 | 2023-03-31 |  | 10% | 76415.0943 | Not yet |  |  |  |  | 76415.0943
7.4

## Sheet1 (hidden)
Project Name | BYD | GAC | RBJAC | BJEV | GAC_Complex Driver | RBJAC | FE-6-A3 | FE3AH | HMI_overhead | AE_overhead | V&V_overhead
Revenue 2021 total (per Project) | 620000 | 672000 | 409200 | 1254229.4 | 2080000 | 1700000 | 1150000
Revenue 2021/01 | 0
Revenue 2021/02
Revenue 2021/03
Revenue 2021/04
Revenue 2021/05
Revenue 2021/06
Revenue 2021/07
Revenue 2021/08
Revenue 2021/09
Revenue 2021/10
Revenue 2021/11
Revenue 2021/12
Vender Cost Reserved | -79200 | 0 | 0 | 0 | 0 | -1550000 | -97200
Vender Cost 01 |  | -4874.84 | 0 | 0 | 0 | 0 | 0 | 0 |  | -32921.9
Vender Cost 02 | [9 empty] | -30033.5
Vender Cost 03
Vender Cost 04
Vender Cost 05
Vender Cost 06
Vender Cost 07
Vender Cost 08
Vender Cost 09
Vender Cost 10
Vender Cost 11
Vender Cost 12
Internal Cost 01
Internal Cost 02
Internal Cost 03
Internal Cost 04
Internal Cost 05
Internal Cost 06
Internal Cost 07
Internal Cost 08
Internal Cost 09
Internal Cost 10
Internal Cost 11
Internal Cost 12

## Sheet2 (hidden)
GE13 | 2019-03-30 | 678867.9 | 2019-03-30 | 1
GE13 | 2019-08-30 | 678867.9 | 2019-08-30 | 1
GE13 | 2019-11-30 | 509150.9 | 2019-11-30 | 1
GE13 | 2020-02-28 | 509150.9 | 2020-02-28 | 1
GE13 | 2020-05-31 | 678867.9 | 2020-05-31 | 1
GE13 | 2020-11-30 | 339434 | 2020-11-30 | 1
GE12B | 2019-07-04 | 358490.57 | 2019-07-04 | 1
GE12B | 2019-08-30 | 448113.21 | 2019-08-30 | 1
GE12B | 2020-02-28 | 89622.64 | 2020-02-28 | 1
FE5AB/6AB | 2020-01-30 | 407337.3585 | 2020-01-30 | 1
FE5AB/6AB | 2020-03-30 | 407337.3585 | 2020-03-30 | 1
FE5AB/6AB | 2020-06-30 | 407337.3585 | 2020-06-30 | 1
FE5AB/6AB | 2020-10-31 | 611006.0377 | 2020-10-31 | 1
FE5AB/6AB | 2021-02-28 | 203668.6792 | 2020-11-04 | 0
FE5AB/6AB | 2020-08-30 | 122641.5094 | 2020-08-30 | 1
FE5AB/6AB | 2020-08-07 | 75471.6981 | 2020-08-07 | 1
FE5AB/6AB | 2020-09-30 | 80188.6792 | 2020-09-30 | 1
UAES | 2019-09-30 | 121500 | 2019-11-30 | 0
UAES | 2019-11-30 | 121500 | 2019-11-30 | 1
BYD | 2019-10-30 | 438679.2453 | 2019-10-30 | 1
BYD | 2020-11-30 | 438679.2453 | 2020-11-30 | 1
BYD | 2021-05-31 | 438679.2453 | 2021-05-31 | 1
BYD | 2021-11-30 | 146226.4151 | 2021-11-30 | 1
GAC | 2019-11-30 | 633962.2642 | 2019-11-30 | 1
GAC | 2020-11-30 | 316981.1321 | 2020-11-30 | 1
GAC | 2021-03-30 | 475471.6981 | 2021-03-30 | 1
GAC | 2021-09-30 | 158490.566 | 2021-09-30 | 1
DFM | 2020-08-15 | 339622.6415 | 2020-08-15 | 1
DFM | 2020-09-30 | 679245.283 | 2020-09-30 | 1
DFM | 2020-12-31 | 113207.5472 | 2020-12-31 | 1
FE3AH | 2020-07-30 | 377357.7358 | 2020-07-30 | 1
FE3AH | 2020-09-30 | 471697.1698 | 2020-09-30 | 1
FE3AH | 2021-03-30 | 94339.434 | 2020-11-04 | 0
RBJAC | 2020-09-30 | 579056.6038 | 2020-09-30 | 1
RBJAC | 2020-11-30 | 965094.3396 | 2020-11-30 | 1
RBJAC | 2021-05-30 | 386037.7358 | 2021-05-30 | 1
BJEV | 2020-12-15 | 208806.2264 | 2020-12-15 | 1
BJEV | 2021-03-15 | 1044031.1321 | 2021-04-30 | 0
BJEV | 2021-09-15 | 139204.1509 | 2021-09-15 | 1
GAC_CDD | 2021-03-01 | 392452.8302 | 2021-03-01 | 1
GAC_CDD | 2021-05-01 | 1177358.4906 | 2021-05-01 | 1
GAC_CDD | 2021-11-01 | 392452.8302 | 2021-11-01 | 1
RBJAC_commercial | 2021-04-01 | 320754.717 | 2021-04-01 | 1
RBJAC_commercial | 2021-05-30 | 801886.7925 | 2021-05-30 | 1
RBJAC_commercial | 2021-12-15 | 481132.0755 | 2021-12-15 | 1

## Billing Status_Digital Projects
Digital Projects Billing Status (W/O. Tax)
Project Name | Milestone | Planned Closure Date | Actual Closure Date | Total Amount | Payment Percentage | Amount (RMB) | Invoicing Status | 2021 Forecast | 2022 Forecast
Hold hope Lite Mes | 1st Phase | 2021-05-05 | 2021-06-17 | 1495000 | 25% | 373750 | Done | 1495000
| 2nd Phase | 2021-08-31 | 2021-10-22 |  | 35% | 523250 | Done
| 3rd Phase | 2021-11-30 | TBD |  | 40% | 598000 | Not yet
Shaohaihui Indus 4.0 Demo Line | 1st Phase | TBD | TBD | 5716455 | 30% | 1714936.5 | Not yet
| 2nd Phase | TBD | TBD |  | 40% | 2286582 | Not yet
| 3rd Phase | TBD | TBD |  | 30% | 1714936.5 | Not yet
Bosch Rexroth PMS | whole porject | 2021-04-30 | 2021-04-30 | 170000 | 100% | 170000 | Done | 170000
Shanghai Jiuzheng Phantom PoC | whole porject | 2021-09-01 | 2021-11-31 | 43610 | 100% | 43610 | Not yet | 43610
1708610
244087.1429

## Profit Estimation
Existing Project
High probability Project
Project | Cost source | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | 2021 Total | 2022+ Total | Overall cost/Rev | vendor cost
AE Testing | 01-Vendor | -27930 | -30033.5 | -33460 | -10080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -101503.5 |  |  | 2206819.73
| 02-RBEI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 03-Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| AE Testing Total | -27930 | -30033.5 | -33460 | -10080 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -101503.5
HMI | 01-Vendor | -36120 | -21210 | -40740 | -16170 | -32690 | -32690 | -32690 | -32690 | -32690 | -32690 | -32690 | -32690 | -375760
| 02-RBEI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 03-Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| HMI Total | -36120 | -21210 | -40740 | -16170 | -32690 | -32690 | -32690 | -32690 | -32690 | -32690 | -32690 | -32690 | -375760
V&V Testing | 01-Vendor | 0 | 0 | -36820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -36820
| 02-RBEI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 03-Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| V&V Testing Total | 0 | 0 | -36820 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -36820
BJEV | 01-Vendor | 0 | 0 | 0 | 0 | -350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -350000
| 02-RBEI | -29012.423 | -30451.089 | -30189.037 | -29884.183 | -29884.183 | -29884.183 | 0 | 0 | 0 | 0 | 0 | 0 | -179305.098
| 03-Revenue | 0 | 0 | 0 | 0 | 1106672.9999 | 0 | 0 | 0 | 147556.4 | 0 | 0 | 0 | 1254229.3999
| BJEV Total | -29012.423 | -30451.089 | -30189.037 | -29884.183 | 726788.8169 | -29884.183 | 0 | 0 | 147556.4 | 0 | 0 | 0 | 724924.3019
BYD | 01-Vendor | 0 | 0 | -8350.12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -8350.12
| 02-RBEI | -14506.2115 | -15225.5445 | -15094.5185 | -14942.0915 | -14942.0915 | -14942.0915 | 0 | 0 | 0 | 0 | 0 | 0 | -89652.549
| 03-Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 465000 | 0 | 0 |  | 0 | 465000
| BYD Total | -14506.2115 | -15225.5445 | -23444.6385 | -14942.0915 | -14942.0915 | -14942.0915 | 0 | 465000 | 0 | 0 | 0 | 0 | 366997.331
DFM | 01-Vendor | -49675.81 | -50062.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -99738.31
| 02-RBEI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 03-Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| DFM Total | -49675.81 | -50062.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -99738.31
FE3AH | 01-Vendor | -41668.25 | -13896.75 | -41235.75 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -96800.75
| 02-RBEI | -14506.2115 | -15225.5445 | -15094.5185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -44826.2745
| 03-Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FE3AH Total | -56174.4615 | -29122.2945 | -56330.2685 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -141627.0245
FE5AB/6AB | 01-Vendor | -26936.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -26936.25
| 02-RBEI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 03-Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| FE5AB/6AB Total | -26936.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -26936.25
GAC | 01-Vendor | -4874.84 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -4874.84
| 02-RBEI | -14506.2115 | -15225.5445 | -15094.5185 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -44826.2745
| 03-Revenue |  |  | 504000 | 0 | 0 | 0 | 0 | 0 | 168000 | 0 | 0 | 0 | 671999.9999
| GAC Total | -19381.0515 | -15225.5445 | 488905.4815 | 0 | 0 | 0 | 0 | 0 | 168000 | 0 | 0 | 0 | 622298.8854
GE13 | 01-Vendor | -56280 | -37000.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -93280.5
| 02-RBEI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 03-Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| GE13 Total | -56280 | -37000.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -93280.5
RBJAC (G2020) | 01-Vendor | 0 | 0 | -2700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2700
| 02-RBEI | -14506.2115 | -15225.5445 | -15094.5185 | -14942.0915 | -14942.0915 | -14942.0915 | 0 | 0 | 0 | 0 | 0 | 0 | -89652.549
| 03-Revenue | 0 | 0 | 0 | 0 | 409199.9999 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 409199.9999
| RBJAC Total | -14506.2115 | -15225.5445 | -17794.5185 | -14942.0915 | 394257.9084 | -14942.0915 | 0 | 0 | 0 | 0 | 0 | 0 | 316847.4509
Geely: FE-6-A3 | 01-Vendor | 0 | 0 | 0 | -3360 | -67285 | -111792.46 | -70987 | -99315.108 | -99315.108 | -99315.108 | -99315.108 | -99315.108 | -750000 |  | -750000
| 02-RBEI | -14506.2115 | -15225.5445 | -15094.5185 | -14942.0915 | -14942.0915 | -14941.0915 | -14940.0915 | -14939.0915 | -14938.0915 | -14937.0915 | -14936.0915 | -14935.0915 | -179277.098 | 45000 | 45000
| 03-Revenue | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345000.002 | 0 | 0 | 0 | 459999.985 | 804999.987 | 200000 | 1004999.987
| FE-6-A3 Total | -14506.2115 | -15225.5445 | -15094.5185 | -18302.0915 | -82227.0915 | -126733.5515 | -85927.0915 | 230745.8025 | -114253.1995 | -114252.1995 | -114251.1995 | 345749.7855 | -124277.111
GAC_CDD | 01-Vendor | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 02-RBEI | -29012.423 | -30451.089 | -30189.037 | -44978.7015 | -59920.793 | -59920.793 | -59920.793 | -59920.793 | -59920.793 | -59920.793 | -59920.793 | -59920.793 | -613997.5945
| 03-Revenue | 0 | 0 | 416000 | 0 | 0 | 0 | 0 | 0 | 1248000.0005 | 0 | 0 | 0 | 1664000.0005
| GAC_CDD Total | -29012.423 | -30451.089 | 385810.963 | -44978.7015 | -59920.793 | -59920.793 | -59920.793 | -59920.793 | 1188079.2075 | -59920.793 | -59920.793 | -59920.793 | 1050002.406 |  | 1800
RBJAC_commercial | 01-Vendor | Jan: 0; Feb: 0; Mar: 0; Apr: -395000; May: -395000; Jun: -395000; Jul: -395000 | -1580000 |  | 1584
| 02-RBEI | -14506.2115 | -15225.5445 | -15094.5185 | -30036.61 | -30036.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -104899.4945 |  | 1360
| 03-Revenue | 0 | 0 | 0 | 340000 | 0 | 1360000.0001 | 0 | 0 | 0 | 0 | 0 | 0 | 1700000.0001
| RBJAC_commercial Total | -14506.2115 | -15225.5445 | -15094.5185 | -85036.61 | -425036.61 | 965000.0001 | -395000 | 0 | 0 | 0 | 0 | 0 | 15100.5056
Audi_Platform | 01-Vendor | 0 | 0 | 0 | 0 |  |  |  |  | 1435175 | 1435175 | 1435175 | 1435175 | 5740700 | 50% | 5740700 | 11481400
| 02-RBEI | 0 | 0 | 0 | 0 | 0 | 0 | -74708.4575 | -74708.4575 | -74708.4575 | -74708.4575 | -74708.4575 | -74708.4575 | -448250.745
| 03-Revenue | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3725000 |  |  | 3725000 | 7450000 | -300000
| Audi_Platform Total | 0 | 0 | 0 | 0 | 0 | 0 | -74708.4575 | -74708.4575 | 5085466.5425 | 1360466.5425 | 1360466.5425 | 5085466.5425 | 12742449.255
Baoneng_EE | 01-Vendor | Jan: 0; Feb: 0; Mar: 0; Apr: 0 | 0
| 02-RBEI | Jan: 0; Feb: 0; Mar: 0; Apr: 0 | 0 | 50%
| 03-Revenue | Jan: 0; Feb: 0; Mar: 0; Apr: 0 | 0
| Baoneng_EE Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Digital_Supporting | 01-Vendor | 0 | 0 | -7116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7116
| Digital_Supporting Total | 0 | 0 | -7116 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -7116
Overhead_Acquisation | 02-RBEI | -145062.115 | -152255.445 | -150945.185 | -140538 | -149420.915 | -149420.915 | -164363.0065 | -164363.0065 | -164363.0065 | -164363.0065 | -164363.0065 | -164363.0065 | -1873820.614 | Gross margin
| Overhead_Acquisation Total | -145062.115 | -152255.445 | -150945.185 | -140538 | -149420.915 | -149420.915 | -164363.0065 | -164363.0065 | -164363.0065 | -164363.0065 | -164363.0065 | -164363.0065 | -1873820.614 | High Act+Commit+Execute | Commit+Execute
VF11-A2 | 01-Vendor
02-RBEI
03-Revenue
VF11-A2 Total
Grand Total |  | -533609.38 | -456714.14 | 447687.76 | -374873.769 | 356809.2244 | 536466.3746 | -812609.3485 | 364063.5455 | 6277795.9439 | 989240.5435 | 989241.5435 | 5174242.5285 | 12957740.8263 | 12957740.8263 | 12590743.4953
11285439.5349
215291.5713
[15 empty] | Rev | costs | vendor | internal
[15 empty] | 31234826.9787 | 8650679 | 5415480 | 3683450
[15 empty] | 4462118.1398 | 1235811.2857 | 773640 | 526207.1429
Note on P62: Author: 1,000,000 as travel fee not confirmed

## Sheet3
[18 empty] | 2021-07-28 |  |  |  |  | 2021-08-09
[10 empty] | GE13 | 2019-03-30 | 678867.9 |  | GE13 | 43554 | 678867.9 | 1 | GE13 | 43554 | 678867.9 | 1 | 1 | GE13 | 43554 | 678867.9 | 1 | 1
[10 empty] | GE13 | 2019-08-30 | 678867.9 |  |  | 43707 | 678867.9 | 1 |  | 43707 | 678867.9 | 1 | 1 |  | 43707 | 678867.9 | 1 | 1
[10 empty] | GE13 | 2019-11-30 | 509150.9 |  |  | 43799 | 509150.9 | 1 |  | 43799 | 509150.9 | 1 | 1 |  | 43799 | 509150.9 | 1 | 1
[10 empty] | GE13 | 2020-02-28 | 509150.9 |  |  | 43889 | 509150.9 | 1 |  | 43889 | 509150.9 | 1 | 1 |  | 43889 | 509150.9 | 1 | 1
[10 empty] | GE13 | 2020-05-31 | 678867.9 |  |  | 43982 | 678867.9 | 1 |  | 43982 | 678867.9 | 1 | 1 |  | 43982 | 678867.9 | 1 | 1
[10 empty] | GE13 | 2020-11-30 | 339434 |  |  | 44165 | 339434 | 1 |  | 44165 | 339434 | 1 | 1 |  | 44165 | 339434 | 1 | 1
[10 empty] | GE12B | 2019-07-04 | 358490.57 |  | GE12B | 43650 | 358490.57 | 1 | GE12B | 43650 | 358490.57 | 1 | 1 | GE12B | 43650 | 358490.57 | 1 | 1
[10 empty] | GE12B | 2019-08-30 | 448113.21 |  |  | 43707 | 448113.21 | 1 |  | 43707 | 448113.21 | 1 | 1 |  | 43707 | 448113.21 | 1 | 1
[10 empty] | GE12B | 2020-02-28 | 89622.64 |  |  | 43889 | 89622.64 | 1 |  | 43889 | 89622.64 | 1 | 1 |  | 43889 | 89622.64 | 1 | 1
[10 empty] | FE5AB/6AB | 2020-01-30 | 407337.3585 |  | FE5AB/6AB | 43860 | 407337.3585 | 1 | FE5AB/6AB | 43860 | 407337.3585 | 1 | 1 | FE5AB/6AB | 43860 | 407337.3585 | 1 | 1
[10 empty] | FE5AB/6AB | 2020-03-30 | 407337.3585 |  |  | 43920 | 407337.3585 | 1 |  | 43920 | 407337.3585 | 1 | 1 |  | 43920 | 407337.3585 | 1 | 1
[10 empty] | FE5AB/6AB | 2020-06-30 | 407337.3585 |  |  | 44012 | 407337.3585 | 1 |  | 44012 | 407337.3585 | 1 | 1 |  | 44012 | 407337.3585 | 1 | 1
[10 empty] | FE5AB/6AB | 2020-10-31 | 611006.0377 |  |  | 44135 | 611006.0377 | 1 |  | 44135 | 611006.0377 | 1 | 1 |  | 44135 | 611006.0377 | 1 | 1
[10 empty] | FE5AB/6AB | 2020-11-04 | 203668.6792 |  |  | 44139 | 203668.6792 | 1 |  | 44139 | 203668.6792 | 1 | 1 |  | 44139 | 203668.6792 | 1 | 1
[10 empty] | FE5AB/6AB | 2020-08-30 | 122641.5094 |  | FE5AB/6AB_Extension | 44073 | 122641.5094 | 1 | FE5AB/6AB_Extension | 44073 | 122641.5094 | 1 | 1 | FE5AB/6AB_Extension | 44073 | 122641.5094 | 1 | 1
[10 empty] | FE5AB/6AB | 2020-08-07 | 75471.6981 |  | FE5AB/6AB_3rd Party_1 | 44050 | 75471.6981 | 1 | FE5AB/6AB_3rd Party_1 | 44050 | 75471.6981 | 1 | 1 | FE5AB/6AB_3rd Party_1 | 44050 | 75471.6981 | 1 | 1
[10 empty] | FE5AB/6AB | 2020-09-30 | 80188.6792 |  | FE5AB/6AB_3rd Party_2 | 44104 | 80188.6792 | 1 | FE5AB/6AB_3rd Party_2 | 44104 | 80188.6792 | 1 | 1 | FE5AB/6AB_3rd Party_2 | 44104 | 80188.6792 | 1 | 1
[10 empty] | UAES | 2019-11-30 | 121500 |  | UAES | - | 121500 | 1 | UAES | - | 121500 | 1 | 1 | UAES | - | 121500 | 1 | 1
[10 empty] | UAES | 2019-11-30 | 121500 |  |  | 43799 | 121500 | 1 |  | 43799 | 121500 | 1 | 1 |  | 43799 | 121500 | 1 | 1
[10 empty] | BYD | 2019-10-30 | 438679.2453 |  | BYD | 43768 | 438679.2453 | 1 | BYD | 43768 | 438679.2453 | 1 | 1 | BYD | 43768 | 438679.2453 | 1 | 1
[10 empty] | BYD | 2020-11-30 | 438679.2453 |  |  | 44165 | 438679.2453 | 1 |  | 44165 | 438679.2453 | 1 | 1 |  | 44165 | 438679.2453 | 1 | 1
[10 empty] | BYD | 2021-05-31 | 438679.2453 |  |  | 44347 | 438679.2453 | 1 |  | 44439 | 438679.2453 | -1 | 1 |  | 44439 | 438679.2453 | 1 | 1
[10 empty] | BYD | 2021-11-30 | 146226.4151 |  |  | 44530 | 146226.4151 | 1 |  | 44620 | 146226.4151 | -1 | 1 |  | 44620 | 146226.4151 | 1 | 1
[10 empty] | GAC | 2019-11-30 | 633962.2642 |  | GAC | 43799 | 633962.2642 | 1 | GAC | 43799 | 633962.2642 | 1 | 1 | GAC | 43799 | 633962.2642 | 1 | 1
[10 empty] | GAC | 2020-11-30 | 316981.1321 |  |  | 44165 | 316981.1321 | 1 |  | 44165 | 316981.1321 | 1 | 1 |  | 44165 | 316981.1321 | 1 | 1
[10 empty] | GAC | 2021-03-30 | 475471.6981 |  |  | 44285 | 475471.6981 | 1 |  | 44285 | 475471.6981 | 1 | 1 |  | 44285 | 475471.6981 | 1 | 1
[10 empty] | GAC | 2021-09-30 | 158490.566 |  |  | 44469 | 158490.566 | 1 |  | 44469 | 158490.566 | 1 | 1 |  | 44469 | 158490.566 | 1 | 1
[10 empty] | DFM | 2020-08-15 | 339622.6415 |  | DFM | 44058 | 339622.6415 | 1 | DFM | 44058 | 339622.6415 | 1 | 1 | DFM | 44058 | 339622.6415 | 1 | 1
[10 empty] | DFM | 2020-09-30 | 679245.283 |  |  | 44104 | 679245.283 | 1 |  | 44104 | 679245.283 | 1 | 1 |  | 44104 | 679245.283 | 1 | 1
[10 empty] | DFM | 2020-12-31 | 113207.5472 |  |  | 44196 | 113207.5472 | 1 |  | 44196 | 113207.5472 | 1 | 1 |  | 44196 | 113207.5472 | 1 | 1
[10 empty] | FE3AH | 2020-07-30 | 377357.7358 |  | FE3AH | 44042 | 377357.7358 | 1 | FE3AH | 44042 | 377357.7358 | 1 | 1 | FE3AH | 44042 | 377357.7358 | 1 | 1
[10 empty] | FE3AH | 2020-09-30 | 471697.1698 |  |  | 44104 | 471697.1698 | 1 |  | 44104 | 471697.1698 | 1 | 1 |  | 44104 | 471697.1698 | 1 | 1
[10 empty] | FE3AH | 2020-11-04 | 94339.434 |  |  | 44139 | 94339.434 | 1 |  | 44139 | 94339.434 | 1 | 1 |  | 44139 | 94339.434 | 1 | 1
[10 empty] | RBJAC | 2020-09-30 | 579056.6038 |  | RBJAC | 44104 | 579056.6038 | 1 | RBJAC | 44104 | 579056.6038 | 1 | 1 | RBJAC | 44104 | 579056.6038 | 1 | 1
[10 empty] | RBJAC | 2020-11-30 | 965094.3396 |  |  | 44165 | 965094.3396 | 1 |  | 44165 | 965094.3396 | 1 | 1 |  | 44165 | 965094.3396 | 1 | 1
[10 empty] | RBJAC | 2021-04-30 | 386037.7358 |  |  | 44316 | 386037.7358 | 1 |  | 44316 | 386037.7358 | 1 | 1 |  | 44316 | 386037.7358 | 1 | 1
[10 empty] | BJEV | 2020-12-15 | 208806.2264 |  | BJEV | 44180 | 208806.2264 | 1 | BJEV | 44180 | 208806.2264 | 1 | 1 | BJEV | 44180 | 208806.2264 | 1 | 1
[10 empty] | BJEV | 2021-05-15 | 1044031.1321 |  |  | 44331 | 1044031.1321 | 1 |  | 44331 | 1044031.1321 | 1 | 1 |  | 44331 | 1044031.1321 | 1 | 1
[10 empty] | BJEV | 2021-09-15 | 139204.1509 |  |  | 44454 | 139204.1509 | 1 |  | 44454 | 139204.1509 | 1 | 1 |  | 44454 | 139204.1509 | 1 | 1
[10 empty] | GAC_Complex Driver | 2021-03-01 | 392452.8302 |  | GAC_Complex Driver | 44256 | 392452.8302 | 1 | GAC_Complex Driver | 44256 | 392452.8302 | 1 | 1 | GAC_Complex Driver | 44256 | 392452.8302 | 1 | 1
[10 empty] | GAC_Complex Driver | 2021-08-01 | 1177358.4906 |  |  | 44409 | 1177358.4906 | 1 |  | 44440 | 1177358.4906 | -1 | 1 |  | 44440 | 1177358.4906 | 1 | 1
[10 empty] | GAC_Complex Driver | 2021-11-01 | 392452.8302 |  |  | 44501 | 392452.8302 | 1 |  | 44621 | 392452.8302 | -1 | 1 |  | 44621 | 392452.8302 | 1 | 1
[10 empty] | RBJAC_commercial | 2021-04-01 | 320754.717 |  | RBJAC_commercial | 44287 | 320754.717 | 1 | RBJAC_commercial | 44287 | 320754.717 | 1 | 1 | RBJAC_commercial | 44287 | 320754.717 | 1 | 1
[10 empty] | RBJAC_commercial | 2021-06-30 | 801886.7925 |  |  | 44377 | 801886.7925 | 1 |  | 44377 | 801886.7925 | 1 | 1 |  | 44377 | 801886.7925 | 1 | 1
[10 empty] | RBJAC_commercial | 2021-06-30 | 481132.0755 |  |  | 44377 | 481132.0755 | 1 |  | 44377 | 481132.0755 | 1 | 1 |  | 44377 | 481132.0755 | 1 | 1
[10 empty] | FE-6-A3 | 2021-08-30 | 325471.6981 |  | FE-6-A3 | 44438 | 325471.6981 | 1 | FE-6-A3 | 44438 | 325471.6981 | 1 | 1 | FE-6-A3 | 44438 | 325471.6981 | 1 | 1
[10 empty] | FE-6-A3 | 2021-12-30 | 433962.2642 |  |  | 44560 | 433962.2642 | 1 |  | 44560 | 433962.2642 | 1 | 1 |  | 44560 | 433962.2642 | 1 | 1
[10 empty] | FE-6-A3 | 2022-06-30 | 216981.1321 |  |  | 44742 | 216981.1321 | 1 |  | 44742 | 216981.1321 | 1 | 1 |  | 44742 | 216981.1321 | 1 | 1
|  | -30451.089 | -30189.037 | -44978.7015 | -59920.793 | -59920.793 | -59920.793 | -59920.793 | -59920.793 | -59920.793 | -59920.793 | -59920.793 |  | AUDI_PPE&CADA&CAPA | 2021-09-30 | 3040080 | -1 | AUDI_PPE&CADA&CAPA | 44469 | 3040080 | 1 | 1 | AUDI_PPE&CADA&CAPA | 44469 | 3040080 | 1 | 1
|  | -15225.5445 | -15094.5185 | -14942.0915 | -14942.0915 | -14941.0915 | -14940.0915 | -14939.0915 | -14938.0915 | -14937.0915 | -14936.0915 | -14935.0915 |  | AUDI_PPE&CADA&CAPA | 2022-01-30 | 3040080 | -1 |  | 44591 | 3040080 | 1 | 1 |  | 44560 | 3040080 | -1 | 1
|  | -30451.089 | -30189.037 | -29884.183 | -29884.183 | -29884.183 | [7 empty] | Baoneng_GX16_EE | 2021-08-30 | 1102641.5094 | -1 | Baoneng_GX16_EE | 44438 | 1102641.5094 | 1 | 1 | Baoneng_GX16_EE | / | 1102641.5094 | -1 | 1
|  | -15225.5445 | -15094.5185 | -14942.0915 | -14942.0915 | -14942.0915 | [7 empty] | Baoneng_GX16_EE | 2021-11-30 | 1102641.5094 | -1 |  | 44530 | 1102641.5094 | 1 | 1 |  | / | 1102641.5094 | -1 | 1
|  | -15225.5445 | -15094.5185 | -14942.0915 | -14942.0915 | -14942.0915 | [7 empty] | Baoneng_GX16_EE | 2022-02-28 | 1102641.5094 | -1 |  | 44620 | 1102641.5094 | 1 | 1 |  | / | 1102641.5094 | -1 | 1
BJEV | 2021-01-01 | 29012.423 | [11 empty] | Baoneng_GX16_EE | 2022-11-30 | 367547.1698 | -1 |  | 44895 | 367547.1698 | 1 | 1 |  | / | 367547.1698 | -1 | 1
BJEV | 2021-02-01 | 30451.089 | [15 empty] | VF11-A2 | 44651 | 305660.3774 | -1 | -1 | VF11-A2 | 44651 | 305660.3774 | 1 | 1
BJEV | 2021-03-01 | 30189.037 | [16 empty] | 44834 | 382075.4717 | -1 | -1 |  | 44834 | 382075.4717 | 1 | 1
BJEV | 2021-04-01 | 29884.183 | [16 empty] | 45016 | 76415.0943 | -1 | -1 |  | 45016 | 76415.0943 | 1 | 1
BJEV | 2021-05-01 | 29884.183
BJEV | 2021-06-01 | 29884.183
BYD | 2021-01-01 | 14506.2115
BYD | 2021-02-01 | 15225.5445
BYD | 2021-03-01 | 15094.5185
BYD | 2021-04-01 | 14942.0915
BYD | 2021-05-01 | 14942.0915
BYD | 2021-06-01 | 14942.0915
FE3AH | 2021-01-01 | 14506.2115
FE3AH | 2021-02-01 | 15225.5445 | [11 empty] | GE13 | 2019-03-30 | 678867.9
FE3AH | 2021-03-01 | 15094.5185 | [11 empty] | GE13 | 2019-08-30 | 678867.9
GAC | 2021-01-01 | 14506.2115 | [11 empty] | GE13 | 2019-11-30 | 509150.9
GAC | 2021-02-01 | 15225.5445 | [11 empty] | GE13 | 2020-02-28 | 509150.9
GAC | 2021-03-01 | 15094.5185 | [11 empty] | GE13 | 2020-05-31 | 678867.9
RBJAC | 2021-01-01 | 14506.2115 | [11 empty] | GE13 | 2020-11-30 | 339434
RBJAC | 2021-02-01 | 15225.5445 | [11 empty] | GE12B | 2019-07-04 | 358490.57
RBJAC | 2021-03-01 | 15094.5185 | [11 empty] | GE12B | 2019-08-30 | 448113.21
RBJAC | 2021-04-01 | 14942.0915 | [11 empty] | GE12B | 2020-02-28 | 89622.64
RBJAC | 2021-05-01 | 14942.0915 | [11 empty] | FE5AB/6AB | 2020-01-30 | 407337.3585
RBJAC | 2021-06-01 | 14942.0915 | [11 empty] | FE5AB/6AB | 2020-03-30 | 407337.3585
FE-6-A3 | 2021-01-01 | 14506.2115 | [11 empty] | FE5AB/6AB | 2020-06-30 | 407337.3585
FE-6-A3 | 2021-02-01 | 15225.5445 | [11 empty] | FE5AB/6AB | 2020-10-31 | 611006.0377
FE-6-A3 | 2021-03-01 | 15094.5185 | [11 empty] | FE5AB/6AB | 2020-11-04 | 203668.6792
FE-6-A3 | 2021-04-01 | 14942.0915 | [11 empty] | FE5AB/6AB_Extension | 2020-08-30 | 122641.5094
FE-6-A3 | 2021-05-01 | 14942.0915 | [11 empty] | FE5AB/6AB_3rd Party_1 | 2020-08-07 | 75471.6981
FE-6-A3 | 2021-06-01 | 14941.0915 | [11 empty] | FE5AB/6AB_3rd Party_2 | 2020-09-30 | 80188.6792
FE-6-A3 | 2021-07-01 | 14940.0915 | [11 empty] | UAES | 2019-11-30 | 121500
FE-6-A3 | 2021-08-01 | 14939.0915 | [11 empty] | UAES | 2019-11-30 | 121500
FE-6-A3 | 2021-09-01 | 14938.0915 | [11 empty] | BYD | 2019-10-30 | 438679.2453
FE-6-A3 | 2021-10-01 | 14937.0915 | [11 empty] | BYD | 2020-11-30 | 438679.2453
FE-6-A3 | 2021-11-01 | 14936.0915 | [11 empty] | BYD | 2021-10-31 | 438679.2453
FE-6-A3 | 2021-12-01 | 14935.0915 | [11 empty] | BYD | 2022-04-30 | 146226.4151
GAC_CDD | 2021-01-01 | 29012.423 | [11 empty] | GAC | 2019-11-30 | 633962.2642
GAC_CDD | 2021-02-01 | 30451.089 | [11 empty] | GAC | 2020-11-30 | 316981.1321
GAC_CDD | 2021-03-01 | 30189.037 | [11 empty] | GAC | 2021-03-30 | 475471.6981
GAC_CDD | 2021-04-01 | 44978.7015 | [11 empty] | GAC | 2021-09-30 | 158490.566
GAC_CDD | 2021-05-01 | 59920.793 | [11 empty] | DFM | 2020-08-15 | 339622.6415
GAC_CDD | 2021-06-01 | 59920.793 | [11 empty] | DFM | 2020-09-30 | 679245.283
GAC_CDD | 2021-07-01 | 59920.793 | [11 empty] | DFM | 2020-12-31 | 113207.5472
GAC_CDD | 2021-08-01 | 59920.793 | [11 empty] | FE3AH | 2020-07-30 | 377357.7358
GAC_CDD | 2021-09-01 | 59920.793 | [11 empty] | FE3AH | 2020-09-30 | 471697.1698
GAC_CDD | 2021-10-01 | 59920.793 | [11 empty] | FE3AH | 2020-11-04 | 94339.434
GAC_CDD | 2021-11-01 | 59920.793 | [11 empty] | RBJAC | 2020-09-30 | 579056.6038
GAC_CDD | 2021-12-01 | 59920.793 | -14506.2115 | [10 empty] | RBJAC | 2020-11-30 | 965094.3396
RBJAC_commercial | 2021-01-01 | 14506.2115 | [11 empty] | RBJAC | 2021-04-30 | 386037.7358
RBJAC_commercial | 2021-02-01 | 15225.5445 | -74708.4575 | [10 empty] | BJEV | 2020-12-15 | 208806.2264
RBJAC_commercial | 2021-03-01 | 15094.5185 | -145062.115 | [7 empty] | -164363.0065 | -164363.0065 | -164363.0065 | BJEV | 2021-05-15 | 1044031.1321
RBJAC_commercial | 2021-04-01 | 30036.61 | [11 empty] | BJEV | 2021-09-15 | 139204.1509
RBJAC_commercial | 2021-05-01 | 30036.61 | [11 empty] | GAC_Complex Driver | 2021-03-01 | 392452.8302
Audi_Platform | 2021-07-01 | 74708.4575 | [11 empty] | GAC_Complex Driver | 2021-10-30 | 1177358.4906
Audi_Platform | 2021-08-01 | 74708.4575 | [11 empty] | GAC_Complex Driver | 2022-04-01 | 392452.8302
Audi_Platform | 2021-09-01 | 74708.4575 | [11 empty] | RBJAC_commercial | 2021-04-01 | 320754.717
Audi_Platform | 2021-10-01 | 74708.4575 | [11 empty] | RBJAC_commercial | 2021-06-30 | 801886.7925
Audi_Platform | 2021-11-01 | 74708.4575 | [11 empty] | RBJAC_commercial | 2021-06-30 | 481132.0755
Audi_Platform | 2021-12-01 | 74708.4575 | [11 empty] | FE-6-A3 | 2021-12-30 | 325471.6981
Baoneng_EE | 2021-06-01 | 14942.0915 | [11 empty] | FE-6-A3 | 2022-04-30 | 433962.2642
Overhead_Acquisation | 2021-01-01 | 145062.115 | [11 empty] | FE-6-A3 | 2022-10-30 | 216981.1321
Overhead_Acquisation | 2021-02-01 | 152255.445 | [11 empty] | AUDI_PPE&CADA&CAPA | 2021-10-30 | 3514150.9434
Overhead_Acquisation | 2021-03-01 | 150945.185 | [11 empty] | AUDI_PPE&CADA&CAPA | 2021-12-30 | 3514150.9434
Overhead_Acquisation | 2021-04-01 | 140538 | [11 empty] | VF11-A2 | 2022-03-31 | 305660.3774
Overhead_Acquisation | 2021-05-01 | 149420.915 | [11 empty] | VF11-A2 | 2022-09-30 | 382075.4717
Overhead_Acquisation | 2021-06-01 | 149420.915 | [11 empty] | VF11-A2 | 2023-03-31 | 76415.0943
Overhead_Acquisation | 2021-07-01 | 164363.0065
Overhead_Acquisation | 2021-08-01 | 164363.0065
Overhead_Acquisation | 2021-09-01 | 164363.0065
Overhead_Acquisation | 2021-10-01 | 164363.0065
Overhead_Acquisation | 2021-11-01 | 164363.0065
Overhead_Acquisation | 2021-12-01 | 164363.0065