## default
>>> Start reading data
engineer | week | date | startTime | endTime | workingHours | overtimeHours | location | worklog
Yan Shujuan | CW36 | 2021-09-01 | 8:43 | 18:10 | 8 | 0 | BOSCH/sgh | 1. TV's BV_LAH image processing 2.0 module requirements and customer features requirements have been reviewed 2. TV's image processing requirements review in progress
Yan Shujuan | CW36 | 2021-09-02 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW36 | 2021-09-03 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW37 | 2021-09-06 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh | 1. All TV requirements documents have been reviewed 2. Training codereader operation 3.Review 6 Chapter of CAPA_AP requirements document has been completed
Yan Shujuan | CW37 | 2021-09-07 | 8:57 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW37 | 2021-09-08 | 8:53 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW37 | 2021-09-09 | 8:51 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW37 | 2021-09-10 | 8:35 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW38 | 2021-09-13 | 8:30 | 18:10 | 8 | 0 | BOSCH/sgh | Review 7-11 Chapter of CAPA_AP requirements document has been completed
Yan Shujuan | CW38 | 2021-09-14 | 8:46 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW38 | 2021-09-15 | 8:43 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW38 | 2021-09-16 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW38 | 2021-09-17 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW38 | 2021-09-18 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW39 | 2021-09-22 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh | 1. Filter Interaction module in CAPA_AP requirements 2. 2 interactive cases have been developed
Yan Shujuan | CW39 | 2021-09-23 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW39 | 2021-09-24 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW39 | 2021-09-26 | 8:30 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW40 | 2021-09-27 | 8:30 | 18:10 | 8 | 0 | BOSCH/sgh | 1.Interaction module completed 6 cases, which have been modified. 2.With function owner to discuss demand issues.
Yan Shujuan | CW40 | 2021-09-28 | 8:46 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW40 | 2021-09-29 | 8:43 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW40 | 2021-09-30 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW41 | 2021-10-08 | 8:57 | 18:10 | 8 | 0 | BOSCH/sgh | 1.CAPA_ AP has developed 16 cases and reviewed 51 requirements
Yan Shujuan | CW41 | 2021-10-09 | 8:35 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW42 | 2021-10-11 | 8:30 | 18:10 | 8 | 0 | BOSCH/sgh | 1.CAPA_ AP has developed 15 cases and reviewed 27 requirements
Yan Shujuan | CW42 | 2021-10-12 | 8:46 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW42 | 2021-10-13 | 8:43 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW42 | 2021-10-14 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW42 | 2021-10-15 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW43 | 2021-10-18 | 8:43 | 18:10 | 8 | 0 | BOSCH/sgh | 1.CAPA_ AP has developed 7 cases and reviewed 35 requirements 2.Write 33 cases in CodeBeamer
Yan Shujuan | CW43 | 2021-10-19 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW43 | 2021-10-20 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW43 | 2021-10-21 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW43 | 2021-10-22 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW44 | 2021-10-25 | 8:30 | 18:10 | 8 | 0 | BOSCH/sgh | 1. CAPA newly developed 14 cases and case of the existing requirement has been developed 2. Write 36 cases in CB 3. Define 13 parameters of cases
Yan Shujuan | CW44 | 2021-10-26 | 8:30 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW44 | 2021-10-27 | 8:46 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW44 | 2021-10-28 | 8:43 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW44 | 2021-10-29 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW45 | 2021-11-01 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh | 1.136 cases have been reviewd and modified, 2.Review training and QA with FO
Yan Shujuan | CW45 | 2021-11-02 | 8:57 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW45 | 2021-11-03 | 8:53 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW45 | 2021-11-04 | 8:51 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW45 | 2021-11-05 | 8:35 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW46 | 2021-11-08 | 8:30 | 18:10 | 8 | 0 | BOSCH/sgh | 1. Revise and review Article 35 cases 2. Review 136 cases and corresponding requirements, written feature, 4 completed
Yan Shujuan | CW46 | 2021-11-09 | 8:46 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW46 | 2021-11-10 | 8:43 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW46 | 2021-11-11 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW46 | 2021-11-12 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW47 | 2021-11-15 | 8:30 | 18:10 | 8 | 0 | BOSCH/sgh | 1. Review requirements and cases, 5 features have been completed 2. 9 features of distance control have been reviewed and modified so far 3. CAPA_ AP parameter definitions are sorted
Yan Shujuan | CW47 | 2021-11-16 | 8:30 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW47 | 2021-11-17 | 8:46 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW47 | 2021-11-18 | 8:43 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW47 | 2021-11-19 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Yan Shujuan | CW48 | 2021-11-22 | 8:30 | 18:10 | 8 | 0 | BOSCH/sgh | 1. After parameter definition, classify, sort and review 2. Confirm with FO that the remaining feature problems have been completed
Yan Shujuan | CW48 | 2021-11-23 | 8:30 | 18:10 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW36 | 2021-09-01 | 8:43 | 18:10 | 8 | 0 | BOSCH/sgh | 1、review008ops document 2、next week continue to check 008 document，and begin to understand CAPA functional requirements
Jiang Hemin | CW36 | 2021-09-02 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW36 | 2021-09-03 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW37 | 2021-09-06 | 8:45 | 18:01 | 8 | 0 | BOSCH/sgh | 1. Complete the translation and correction of the 008 document and submit it to the Audi engineer; 2. Learn Codebeamer operation 3.Review CAPA_AP requirements document
Jiang Hemin | CW37 | 2021-09-07 | 8:57 | 18:05 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW37 | 2021-09-08 | 8:53 | 18:08 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW37 | 2021-09-09 | 8:51 | 18:45 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW37 | 2021-09-10 | 8:56 | 18:04 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW38 | 2021-09-13 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh | Review 6-11 Chapter of CAPA_AP requirements document has been completed
Jiang Hemin | CW38 | 2021-09-14 | 8:46 | 18:10 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW38 | 2021-09-15 | 8:43 | 18:10 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW38 | 2021-09-16 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW38 | 2021-09-17 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW38 | 2021-09-18 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW39 | 2021-09-22 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh | Screening HMI-related requirements that are not covered by test cases, and initial classification of requirements
Jiang Hemin | CW39 | 2021-09-23 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW39 | 2021-09-24 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW39 | 2021-09-26 | 8:30 | 18:10 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW40 | 2021-09-27 | 8:30 | 18:10 | 8 | 0 | BOSCH/sgh | HMI module completed 11 cases, 9 of which have been modified
Jiang Hemin | CW40 | 2021-09-28 | 8:46 | 18:10 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW40 | 2021-09-29 | 8:43 | 18:10 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW41 | 2021-10-08 | 8:51 | 18:45 | 8 | 0 | BOSCH/sgh | CAPA_ AP has developed 10 cases and reviewed 21 requirements
Jiang Hemin | CW41 | 2021-10-09 | 8:56 | 18:04 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW42 | 2021-10-11 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh | CAPA_ AP has developed 11 cases and reviewed 26 requirements
Jiang Hemin | CW42 | 2021-10-12 | 8:46 | 18:10 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW42 | 2021-10-13 | 8:43 | 18:10 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW42 | 2021-10-14 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW42 | 2021-10-15 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW43 | 2021-10-18 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh | 1.CAPA_ AP has developed 4 cases and reviewed 20 requirements 2.Write 8 cases in CodeBeamer
Jiang Hemin | CW43 | 2021-10-19 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW43 | 2021-10-20 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW43 | 2021-10-21 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW43 | 2021-10-22 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW44 | 2021-10-25 | 8:30 | 18:10 | 8 | 0 | BOSCH/sgh | 1. CAPA newly developed 13 cases 2. Add requirement IDs to 7 cases existed and modified 3. Write 20 cases in CB 4. Define 16 parameters of cases
Jiang Hemin | CW44 | 2021-10-26 | 8:30 | 18:10 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW44 | 2021-10-27 | 8:46 | 18:10 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW44 | 2021-10-28 | 8:43 | 18:10 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW44 | 2021-10-29 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW45 | 2021-11-01 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh | 1.136 cases have been reviewd and modified, 2.Review training and QA with FO
Jiang Hemin | CW45 | 2021-11-02 | 8:57 | 18:10 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW45 | 2021-11-03 | 8:53 | 18:10 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW45 | 2021-11-04 | 8:51 | 18:10 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW46 | 2021-11-08 | 8:30 | 18:10 | 8 | 0 | BOSCH/sgh | 1. Revise and review Article 35 cases 2. Review 136 cases and corresponding requirements, written feature, 4 completed
Jiang Hemin | CW46 | 2021-11-09 | 8:46 | 18:10 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW46 | 2021-11-10 | 8:43 | 18:10 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW46 | 2021-11-11 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW46 | 2021-11-12 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW47 | 2021-11-15 | 8:30 | 18:10 | 8 | 0 | BOSCH/sgh | 1. Review requirements and cases, 5 features have been completed 2. 9 features of distance control have been reviewed and modified so far 3. CAPA_ AP parameter definitions are sorted and classified
Jiang Hemin | CW47 | 2021-11-16 | 8:46 | 18:10 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW47 | 2021-11-17 | 8:43 | 18:10 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW47 | 2021-11-18 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW47 | 2021-11-19 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Jiang Hemin | CW48 | 2021-11-22 | 8:46 | 18:10 | 8 | 0 | BOSCH/sgh | 1. After parameter definition, classify, sort and review 2. Confirm with FO that the remaining feature problems have been completed
Jiang Hemin | CW48 | 2021-11-23 | 8:43 | 18:10 | 8 | 0 | BOSCH/sgh
Dai Fang | CW36 | 2021-09-01 | 8:43 | 18:10 | 8 | 0 | BOSCH/sgh | 1. Modify the test case of OPS & APS； 2. Define the parameters of LH China specific test case； 3. Define the Obstacles in Codebeamer.
Dai Fang | CW36 | 2021-09-02 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Dai Fang | CW36 | 2021-09-03 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Dai Fang | CW37 | 2021-09-06 | 8:55 | 17:40 | 8 | 0 | BOSCH/sgh | 1. Define the Sektors of PDC decetion and parameters 2. Classify test cases according to the document structure.
Dai Fang | CW37 | 2021-09-07 | 8:57 | 17:40 | 8 | 0 | BOSCH/sgh
Dai Fang | CW37 | 2021-09-08 | 8:53 | 17:40 | 8 | 0 | BOSCH/sgh
Dai Fang | CW37 | 2021-09-09 | 8:40 | 17:40 | 8 | 0 | BOSCH/sgh
Dai Fang | CW37 | 2021-09-10 | 8:50 | 17:40 | 8 | 0 | BOSCH/sgh
Dai Fang | CW38 | 2021-09-13 | 8:30 | 18:10 | 8 | 0 | BOSCH/sgh | Edit test case of 5.1.1 Obstacles detection with stationary Ego in CodeBeamer.
Dai Fang | CW38 | 2021-09-14 | 8:46 | 17:40 | 8 | 0 | BOSCH/sgh
Dai Fang | CW38 | 2021-09-15 | 8:43 | 18:10 | 8 | 0 | BOSCH/sgh
Dai Fang | CW38 | 2021-09-16 | 8:55 | 18:00 | 8 | 0 | BOSCH/sgh
Dai Fang | CW38 | 2021-09-17 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Dai Fang | CW38 | 2021-09-18 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Dai Fang | CW39 | 2021-09-22 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh | Edit test case of speed hump detection with dynamic Ego in CodeBeamer.
Dai Fang | CW39 | 2021-09-23 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Dai Fang | CW39 | 2021-09-24 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Dai Fang | CW39 | 2021-09-26 | 8:30 | 18:10 | 8 | 0 | BOSCH/sgh
Dai Fang | CW40 | 2021-09-27 | 8:30 | 18:10 | 8 | 0 | BOSCH/sgh | 1、Modify the parameters and test case of speed hump detection with dynamic Ego； 2、Edit test case of 5.2 OPS.
Dai Fang | CW40 | 2021-09-28 | 8:46 | 18:10 | 8 | 0 | BOSCH/sgh
Dai Fang | CW40 | 2021-09-29 | 8:43 | 18:10 | 8 | 0 | BOSCH/sgh
Dai Fang | CW40 | 2021-09-30 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Dai Fang | CW41 | 2021-10-08 | 8:53 | 17:40 | 8 | 0 | BOSCH/sgh | 1、Modify the discrisption of obstacle detection； 2、Finished the test case of OPS.
Dai Fang | CW41 | 2021-10-09 | 8:50 | 17:40 | 8 | 0 | BOSCH/sgh
Dai Fang | CW42 | 2021-10-11 | 8:30 | 18:10 | 8 | 0 | BOSCH/sgh | 1、Edit test case of APS(5.3)； 2、Edit the test case of Other requirements(5.1.3).
Dai Fang | CW42 | 2021-10-12 | 8:46 | 17:40 | 8 | 0 | BOSCH/sgh
Dai Fang | CW42 | 2021-10-13 | 8:43 | 18:10 | 8 | 0 | BOSCH/sgh
Dai Fang | CW42 | 2021-10-14 | 8:55 | 18:00 | 8 | 0 | BOSCH/sgh
Dai Fang | CW42 | 2021-10-15 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Dai Fang | CW43 | 2021-10-18 | 8:55 | 18:00 | 8 | 0 | BOSCH/sgh
Dai Fang | CW43 | 2021-10-19 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh | Edit 36 test cases abot obstcale detection, eg. ground lock on, ground lock off, stop bar and so on.
Dai Fang | CW43 | 2021-10-20 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Dai Fang | CW43 | 2021-10-21 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Dai Fang | CW43 | 2021-10-22 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Dai Fang | CW44 | 2021-10-25 | 8:30 | 18:10 | 8 | 0 | BOSCH/sgh | Edit 72 test cases abot obstcale detection, eg. bicycle, electric bicycle, elderlymobility scooter, fence and so on.
Dai Fang | CW44 | 2021-10-26 | 8:30 | 18:10 | 8 | 0 | BOSCH/sgh
Dai Fang | CW44 | 2021-10-27 | 8:46 | 18:10 | 8 | 0 | BOSCH/sgh
Dai Fang | CW44 | 2021-10-28 | 8:43 | 18:10 | 8 | 0 | BOSCH/sgh
Dai Fang | CW44 | 2021-10-29 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Dai Fang | CW45 | 2021-11-01 | 8:30 | 18:10 | 8 | 0 | BOSCH/sgh | 1. 24 obstacle detection test cases were edited 2. 50 test scenarios were drawn.
Dai Fang | CW45 | 2021-11-02 | 8:30 | 18:10 | 8 | 0 | BOSCH/sgh
Dai Fang | CW45 | 2021-11-03 | 8:46 | 18:10 | 8 | 0 | BOSCH/sgh
Dai Fang | CW45 | 2021-11-04 | 8:43 | 18:10 | 8 | 0 | BOSCH/sgh
Dai Fang | CW45 | 2021-11-05 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Dai Fang | CW46 | 2021-11-08 | 8:30 | 18:10 | 8 | 0 | BOSCH/sgh | Review 102 test case of APS & OPS.
Dai Fang | CW46 | 2021-11-09 | 8:46 | 18:10 | 8 | 0 | BOSCH/sgh
Dai Fang | CW46 | 2021-11-10 | 8:43 | 18:10 | 8 | 0 | BOSCH/sgh
Dai Fang | CW46 | 2021-11-11 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Dai Fang | CW46 | 2021-11-12 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Dai Fang | CW47 | 2021-11-15 | 8:30 | 18:10 | 8 | 0 | BOSCH/sgh | 1、Review 88 test case of APS & OPS; 2、Review 20 test case of AEB-PR from German engineer.
Dai Fang | CW47 | 2021-11-16 | 8:46 | 18:10 | 8 | 0 | BOSCH/sgh
Dai Fang | CW47 | 2021-11-17 | 8:43 | 18:10 | 8 | 0 | BOSCH/sgh
Dai Fang | CW47 | 2021-11-18 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Dai Fang | CW47 | 2021-11-19 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Dai Fang | CW48 | 2021-11-22 | 8:30 | 18:10 | 8 | 0 | BOSCH/sgh | Review 50 test case of AEB-PR from German engineer.
Dai Fang | CW48 | 2021-11-23 | 8:46 | 18:10 | 8 | 0 | BOSCH/sgh
Zhong Wei | CW36 | 2021-09-01 | 8:43 | 18:10 | 8 | 0 | BOSCH/sgh | Use RoadDesign to draw Roadgraph high-speed test scene，Every Monday and Wednesday afternoon group meeting to discuss Roadgraph test scenarios
Zhong Wei | CW36 | 2021-09-02 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Zhong Wei | CW36 | 2021-09-03 | 8:55 | 18:10 | 8 | 0 | BOSCH/sgh
Zhong Wei | CW37 | 2021-09-06 | 8:25 | 17:30 | 8 | 0 | MA/ACB | 1、Write Roadgraph highway test scenarios， 2、Learn CAPL language design independently.
Zhong Wei | CW37 | 2021-09-07 | 8:33 | 17:36 | 8 | 0 | MA/ACB
Zhong Wei | CW37 | 2021-09-08 | 8:35 | 17:30 | 8 | 0 | MA/ACB
Zhong Wei | CW37 | 2021-09-09 | 8:35 | 18:07 | 8 | 0 | MA/ACB
Zhong Wei | CW37 | 2021-09-10 | 8:25 | 17:40 | 8 | 0 | MA/ACB
Zhong Wei | CW38 | 2021-09-13 | 8:45 | 17:32 | 8 | 0 | MA/ACB | 1、Write Roadgraph highway test scenarios.2、Self-learning simulation project compilation and debugging 3、Assist Luo Tairan in the parking test, test the rear view and TOP view of A3
Zhong Wei | CW38 | 2021-09-14 | 8:46 | 17:47 | 8 | 0 | MA/ACB
Zhong Wei | CW38 | 2021-09-15 | 8:43 | 17:41 | 8 | 0 | MA/ACB
Zhong Wei | CW38 | 2021-09-16 | 8:50 | 17:40 | 8 | 0 | MA/ACB
Zhong Wei | CW38 | 2021-09-17 | 8:30 | 17:31 | 8 | 0 | MA/ACB
Zhong Wei | CW38 | 2021-09-18 | 8:30 | 17:31 | 8 | 0 | MA/ACB
Zhong Wei | CW39 | 2021-09-22 | 7:34 | 17:35 | 8 | 0 | MA/ACB | 1、Self-learning CAN simulation
Zhong Wei | CW39 | 2021-09-23 | 8:35 | 17:40 | 8 | 0 | MA/ACB
Zhong Wei | CW39 | 2021-09-24 | 8:45 | 17:40 | 8 | 0 | MA/ACB
Zhong Wei | CW39 | 2021-09-26 | 8:30 | 18:10 | 8 | 0 | MA/ACB
Zhong Wei | CW40 | 2021-09-27 | 8:30 | 18:10 | 8 | 0 | MA/ACB | 1 、Support Luo Tairan Parking test, test ASUV's REAR view and TOP view 2、Self-learning CAN+LIN emulation
Zhong Wei | CW40 | 2021-09-28 | 8:46 | 18:10 | 8 | 0 | MA/ACB
Zhong Wei | CW40 | 2021-09-29 | 8:43 | 18:10 | 8 | 0 | MA/ACB
Zhong Wei | CW40 | 2021-09-30 | 8:55 | 18:10 | 8 | 0 | MA/ACB
Zhong Wei | CW41 | 2021-10-08 | 8:35 | 17:30 | 8 | 0 | MA/ACB | Support Wang Rongting's Parking test, test the rear view of A SUVe
Zhong Wei | CW41 | 2021-10-09 | 8:25 | 17:40 | 8 | 0 | MA/ACB
Zhong Wei | CW42 | 2021-10-11 | 8:45 | 17:32 | 8 | 0 | MA/ACB | Support Wang Rongting's Parking test, test the rear view of A SUVe
Zhong Wei | CW42 | 2021-10-12 | 8:46 | 17:47 | 8 | 0 | MA/ACB
Zhong Wei | CW42 | 2021-10-13 | 8:43 | 17:41 | 8 | 0 | MA/ACB
Zhong Wei | CW42 | 2021-10-14 | 8:50 | 17:40 | 8 | 0 | MA/ACB
Zhong Wei | CW42 | 2021-10-15 | 8:30 | 17:31 | 8 | 0 | MA/ACB
Zhong Wei | CW43 | 2021-10-18 | 8:50 | 17:40 | 8 | 0 | MA/ACB | 1.Install software on the new workstation,try-run PSD DE version on the new workstation.2,Support Wang Rongting's Parking test, test the rear view of A+ SUVe
Zhong Wei | CW43 | 2021-10-19 | 8:30 | 17:31 | 8 | 0 | MA/ACB
Zhong Wei | CW43 | 2021-10-20 | 7:34 | 17:35 | 8 | 0 | MA/ACB
Zhong Wei | CW43 | 2021-10-21 | 8:35 | 17:40 | 8 | 0 | MA/ACB
Zhong Wei | CW43 | 2021-10-22 | 8:45 | 17:40 | 8 | 0 | MA/ACB
Zhong Wei | CW44 | 2021-10-25 | 8:30 | 18:10 | 8 | 0 | MA/ACB | .Support Wang Rongting's Parking test, test the rear view of A+ SUVe
Zhong Wei | CW44 | 2021-10-26 | 8:30 | 18:10 | 8 | 0 | MA/ACB
Zhong Wei | CW44 | 2021-10-27 | 8:46 | 18:10 | 8 | 0 | MA/ACB
Zhong Wei | CW44 | 2021-10-28 | 8:43 | 18:10 | 8 | 0 | MA/ACB
Zhong Wei | CW44 | 2021-10-29 | 8:55 | 18:10 | 8 | 0 | MA/ACB
Zhong Wei | CW45 | 2021-11-01 | 8:53 | 18:10 | 8 | 0 | MA/ACB | 1.Rear view retest of EF076 2.Retest of EF075 Top view 3. EF055 vehicle preparation
Zhong Wei | CW45 | 2021-11-02 | 8:57 | 18:10 | 8 | 0 | MA/ACB
Zhong Wei | CW45 | 2021-11-03 | 8:58 | 18:10 | 8 | 0 | MA/ACB
Zhong Wei | CW45 | 2021-11-04 | 8:50 | 18:10 | 8 | 0 | MA/ACB
Zhong Wei | CW45 | 2021-11-05 | 8:55 | 18:10 | 8 | 0 | MA/ACB
Zhong Wei | CW46 | 2021-11-08 | 8:52 | 18:10 | 8 | 0 | MA/ACB | 1 EF075 top view of the retest. 2.EF055 rear view test.
Zhong Wei | CW46 | 2021-11-09 | 8:57 | 18:10 | 8 | 0 | MA/ACB
Zhong Wei | CW46 | 2021-11-10 | 8:58 | 18:10 | 8 | 0 | MA/ACB
Zhong Wei | CW46 | 2021-11-11 | 9:00 | 18:10 | 8 | 0 | MA/ACB
Zhong Wei | CW46 | 2021-11-12 | 8:55 | 18:10 | 8 | 0 | MA/ACB
Zhong Wei | CW47 | 2021-11-15 | 8:52 | 17:40 | 8 | 0 | MA/ACB | 1. EF066 top view test.
Zhong Wei | CW47 | 2021-11-16 | 8:57 | 17:45 | 8 | 0 | MA/ACB
Zhong Wei | CW47 | 2021-11-17 | 8:30 | 18:10 | 8 | 0 | —— | On standby
Zhong Wei | CW47 | 2021-11-18 | 8:46 | 18:10 | 8 | 0 | —— | On standby
Zhong Wei | CW47 | 2021-11-19 | 8:43 | 18:10 | 8 | 0 | —— | On standby
Zhong Wei | CW48 | 2021-11-22 | 8:30 | 18:10 | 8 | 0 | —— | On standby
Zhong Wei | CW48 | 2021-11-23 | 8:46 | 18:10 | 8 | 0 | —— | On standby
Zhong Wei | CW48 | 2021-11-24 | 8:12 | 12:10 | 4 | 0 | —— | On standby
Wu Peng | CW36 | 2021-09-01 | 8:43 | 18:10 | 8 | 0 | MA/ACB | 1. Zhaoyuan (A6LMA_PCB test, it's sop related) test. 2. (A6LMA_PCB test, it's sop related) report analysis
Wu Peng | CW36 | 2021-09-02 | 8:55 | 17:58 | 8 | 0 | MA/ACB
Wu Peng | CW36 | 2021-09-03 | 8:55 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW37 | 2021-09-06 | 8:35 | 18:10 | 8 | 0 | MA/ACB | (A6LMA_PCB test, it's sop related) test report analysis
Wu Peng | CW37 | 2021-09-07 | 8:40 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW37 | 2021-09-08 | 8:43 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW37 | 2021-09-09 | 8:45 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW37 | 2021-09-10 | 8:45 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW38 | 2021-09-13 | 8:30 | 18:10 | 8 | 0 | MA/ACB | 1.(A6LMA_PCB test, it's sop related) test report analysis 2. Assist Luo Tairan in the parking test and test the rear view of A3. 3. Receive Audi vehicles 4. A+SUVe ME3 PSF CNCAP&CIASI report analysis
Wu Peng | CW38 | 2021-09-14 | 8:46 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW38 | 2021-09-15 | 8:43 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW38 | 2021-09-16 | 8:55 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW38 | 2021-09-17 | 8:55 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW38 | 2021-09-18 | 8:55 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW39 | 2021-09-22 | 8:55 | 18:10 | 8 | 0 | MA/ACB | 1.(A6LMA_PCB test, it's sop related) test report analysis 2. A+SUVe ME3 PSF CNCAP&CIASI report analysis
Wu Peng | CW39 | 2021-09-23 | 8:55 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW39 | 2021-09-24 | 8:55 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW39 | 2021-09-26 | 8:30 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW40 | 2021-09-27 | 8:30 | 18:10 | 8 | 0 | MA/ACB | 1.A+SUVe PSF C-NCAP（CCRS、CCRS、TW、PTA、）test
Wu Peng | CW40 | 2021-09-28 | 8:46 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW40 | 2021-09-29 | 8:43 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW40 | 2021-09-30 | 8:55 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW41 | 2021-10-08 | 8:43 | 18:10 | 8 | 0 | MA/ACB | BSD_TW overtaking，BSD_Vehicle overtaking，BSD_Vehicle merging，BSD_Vehicle merging+overtaking，BSD_double Vehicle overtaking，BSD_TW merging test report analysis
Wu Peng | CW41 | 2021-10-09 | 8:45 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW42 | 2021-10-11 | 8:30 | 18:10 | 8 | 0 | MA/ACB | BSD_TW overtaking，BSD_Vehicle overtaking，BSD_Vehicle merging，BSD_Vehicle merging+overtaking，BSD_double Vehicle overtaking，BSD_TW merging test report analysis
Wu Peng | CW42 | 2021-10-12 | 8:46 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW42 | 2021-10-13 | 8:43 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW42 | 2021-10-14 | 8:55 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW42 | 2021-10-15 | 8:55 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW43 | 2021-10-18 | 8:55 | 18:10 | 8 | 0 | MA/ACB | 1. BSD_TW overtaking, BSD_Vehicle overtaking, BSD_Vehicle merging, BSD_Vehicle merging+overtaking, BSD_double Vehicle overtaking, BSD_TW merging test report analysis 2. EF348 prepares the vehicle and charges. 3. EF076 prepares the vehicle and charges.
Wu Peng | CW43 | 2021-10-19 | 8:55 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW43 | 2021-10-20 | 8:55 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW43 | 2021-10-21 | 8:55 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW43 | 2021-10-22 | 8:55 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW44 | 2021-10-25 | 8:30 | 18:10 | 8 | 0 | MA/ACB | 1. A+SUVe_ME3_RCTA_analysis report collation. 2. Statistics_RCAT_AU316_3CS_89D_Sline_0284_ME3 report sorting. 3. A+SUVe_ME3_ASW_analysis report collation. 4. Statistics_ASW_AU316_3CS_89D_Sline_0284_ME3 report sorting. 5. A+SUVe_ME3_SWA_analysis report collation. 6. Statistics_SWA_AU316_3CS_89D_Sline_0284_ME3 report finishing. 7. A6LMA_CNCAP_Test_Result report is organized. 8. Prepare EF076 vehicles before testing.
Wu Peng | CW44 | 2021-10-26 | 8:30 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW44 | 2021-10-27 | 8:46 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW44 | 2021-10-28 | 8:43 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW44 | 2021-10-29 | 8:55 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW45 | 2021-11-01 | 8:53 | 18:10 | 8 | 0 | MA/ACB | 1. Statistics_RCAT_AU316_3CS_89D_Sline_0284_ME3 report sorting. 2. A+SUVe_ME3_ASW_analysis report collation. 3. Statistics_ASW_AU316_3CS_89D_Sline_0284_ME3 report sorting. 4. A+SUVe_ME3_SWA_analysis report collation. 5. Statistics_SWA_AU316_3CS_89D_Sline_0284_ME3 report finishing. 6. A6LMA_CNCAP_Test_Result report is organized. 7. Prepare EF076 vehicles before testing.
Wu Peng | CW45 | 2021-11-02 | 8:57 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW45 | 2021-11-03 | 8:58 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW45 | 2021-11-04 | 8:50 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW45 | 2021-11-05 | 8:55 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW46 | 2021-11-08 | 8:55 | 18:10 | 8 | 0 | MA/ACB | 1. A+SUVe_ME3_PSF on-site road test
Wu Peng | CW46 | 2021-11-09 | 8:57 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW46 | 2021-11-10 | 8:58 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW46 | 2021-11-11 | 8:50 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW46 | 2021-11-12 | 8:55 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW47 | 2021-11-15 | 8:53 | 18:10 | 8 | 0 | MA/ACB | 1、A+SUVe_ME3_PSF report sorting
Wu Peng | CW47 | 2021-11-16 | 8:57 | 18:10 | 8 | 0 | MA/ACB
Wu Peng | CW47 | 2021-11-17 | 8:58 | 18:10 | 8 | 0 | —— | On standby
Wu Peng | CW47 | 2021-11-18 | 8:50 | 18:10 | 8 | 0 | —— | On standby
Wu Peng | CW47 | 2021-11-19 | 8:55 | 18:10 | 8 | 0 | —— | On standby
Wu Peng | CW48 | 2021-11-22 | 8:30 | 18:10 | 8 | 0 | —— | On standby
Wu Peng | CW48 | 2021-11-23 | 8:46 | 18:10 | 8 | 0 | —— | On standby
Wu Peng | CW48 | 2021-11-24 | 8:12 | 12:10 | 4 | 0 | —— | On standby
Ding Xiuju | CW36 | 2021-09-01 | 8:43 | 18:10 | 8 | 0 | MA/ACB | 1、review008ops document 2、next Monday continue to check 008 document
Ding Xiuju | CW36 | 2021-09-02 | 8:55 | 18:10 | 8 | 0 | MA/ACB
Ding Xiuju | CW36 | 2021-09-03 | 8:55 | 18:10 | 8 | 0 | MA/ACB
Zhao Wenlong | CW28 | 2021-07-05 | 9:00 | 17:30 | 8h | 0 | MA/ACB | 1、Parking 测试文档梳理； 2、与Parking 工程师对接具体工作事项
Zhao Wenlong | CW28 | 2021-07-06 | 9:00 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW28 | 2021-07-07 | 9:00 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW28 | 2021-07-08 | 9:00 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW28 | 2021-07-09 | 9:00 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW29 | 2021-07-12 | 9:00 | 17:30 | 8h | 0 | MA/ACB | 1、Test case 阅读； 2、实车测试现场任务及人员的协调
Zhao Wenlong | CW29 | 2021-07-13 | 9:00 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW29 | 2021-07-14 | 9:00 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW29 | 2021-07-15 | 9:00 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW29 | 2021-07-16 | 9:00 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW30 | 2021-07-19 | 9:00 | 17:30 | 8h | 0 | MA/ACB | 1、A7L测试车辆及测试设备确认与Audi 文汐； 2、参加Tairan Parking&drving meeting，及后续工作安排
Zhao Wenlong | CW30 | 2021-07-20 | 9:00 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW30 | 2021-07-21 | 9:00 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW30 | 2021-07-22 | 9:00 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW30 | 2021-07-23 | 9:00 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW31 | 2021-07-26 | 9:00 | 17:30 | 8h | 0 | MA/ACB | 1、055试验车软件刷写、车辆状态确认、Rear view测试 2、Audi软件安装流程推动
Zhao Wenlong | CW31 | 2021-07-27 | 9:00 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW31 | 2021-07-28 | 9:00 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW31 | 2021-07-29 | 9:00 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW31 | 2021-07-30 | 9:00 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW32 | 2021-08-02 | 8:40 | 17:30 | 8h | 0 | MA/ACB | 1、Audi card apply for everyone 100% 2、Paco channle code Reading for A+SUVe EF055 and check the marked adaption is set to automatisch 100%; 3、A6L issue meeting and need to analysis the signal for question , finshed the work next week. 30% 4、workshop for C-BEV rifitting with SW&ZDC flashing 80% 5、RT & RT Range meeting 100% 6、test results review with CANape for A6LMA driving 505
Zhao Wenlong | CW32 | 2021-08-03 | 8:50 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW32 | 2021-08-04 | 8:48 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW32 | 2021-08-05 | 8:45 | 17:35 | 8h | 0 | MA/ACB
Zhao Wenlong | CW32 | 2021-08-06 | 8:45 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW33 | 2021-08-09 | 8:40 | 17:30 | 8h | 0 | MA/ACB | 1、A6L from Tianjing to Beijing, the transportation is over. 2、contact the SVW&FAW parking test engineers will be have a skype meeting about review the test plan 30%; with Xi Jianpo talk about the Parking test plan 90% 3、C-BEV status conform and check 50% 4、meeting with fonction owner talk about the A7L RPA test plan and go to the shanghai SVW 70% 5、writing report of rear view test of A+SUV 100% 6、jion the A7L RPA meeting every day
Zhao Wenlong | CW33 | 2021-08-10 | 8:50 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW33 | 2021-08-11 | 8:48 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW33 | 2021-08-12 | 8:45 | 17:35 | 8h | 0 | MA/ACB
Zhao Wenlong | CW33 | 2021-08-13 | 8:45 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW34 | 2021-08-16 | 8:40 | 17:30 | 8h | 0 | MA/ACB | 1、A7L VZE function testing in tianjin 100%: 2、MLB parking testing meeting of cluster 3.3 with tickets，disscuss how to test the tickets cases 50%; 3、A7L parking testing in shanghai and correctly the work of Bosch engineer 100%;
Zhao Wenlong | CW34 | 2021-08-17 | 8:50 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW34 | 2021-08-18 | 8:48 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW34 | 2021-08-19 | 9:00 | 22:00 | 12.5h | 4.5 | MA/ACB
Zhao Wenlong | CW34 | 2021-08-20 | 8:00 | 19:00 | 10h | 2 | MA/ACB
Zhao Wenlong | CW34 | 2021-08-21 | 8:00 | 19:00 | 4h | 4 | MA/ACB
Zhao Wenlong | CW35 | 2021-08-23 | 8:40 | 17:30 | 8h | 0 | MA/ACB | 1、cluster 3.3 parking test preparation with xijianpo; 2、A6L MA parking test preparation with xijianpo; 3、C SUV parking test meeting about how to test the function; 4、Finding the vehicle that the IPA function is ok and try to do it .
Zhao Wenlong | CW35 | 2021-08-24 | 8:50 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW35 | 2021-08-25 | 8:30 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW35 | 2021-08-26 | 8:45 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW35 | 2021-08-27 | 8:40 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW36 | 2021-08-30 | 8:40 | 17:30 | 8h | 0 | MA/ACB | 1、cluster 3.3 parking test preparation with xijianpo; 2、meeting with FAW-VW about cluster3.3 parking test and record 3、talk about the PDC&IPA test case with wenxi and FO 100% 4、A+SUVe vehicle preparation with status for function
Zhao Wenlong | CW36 | 2021-08-31 | 8:50 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW36 | 2021-09-01 | 8:30 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW36 | 2021-09-02 | 8:45 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW36 | 2021-09-03 | 8:40 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW37 | 2021-09-06 | 8:40 | 17:30 | 8h | 0 | MA/ACB | 1、cluster 3.3 parking test preparation with xijianpo; 2、A+SUVe vehicle preparation with status for function
Zhao Wenlong | CW37 | 2021-09-07 | 8:50 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW37 | 2021-09-08 | 8:30 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW37 | 2021-09-09 | 8:45 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW37 | 2021-09-10 | 8:40 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW38 | 2021-09-12 | 8:40 | 17:30 | 8h | 8 | shanghai | 1、A+SUVe parking test in shanghai and task has been finished 65%;
Zhao Wenlong | CW38 | 2021-09-13 | 8:50 | 17:30 | 8h | 0 | shanghai
Zhao Wenlong | CW38 | 2021-09-14 | 8:30 | 17:30 | 8h | 0 | shanghai
Zhao Wenlong | CW38 | 2021-09-15 | 8:45 | 17:30 | 8h | 0 | shanghai
Zhao Wenlong | CW38 | 2021-09-16 | 8:30 | 17:30 | 8h | 0 | shanghai
Zhao Wenlong | CW38 | 2021-09-17 | 8:45 | 17:30 | 8h | 0 | shanghai
Zhao Wenlong | CW38 | 2021-09-18 | 8:40 | 17:30 | 8h | 0 | shanghai
Zhao Wenlong | CW39 | 2021-09-22 | 8:40 | 17:30 | 8h | 0 | shanghai | 1、A+SUVe parking test in shanghai and task has been finished 85%;
Zhao Wenlong | CW39 | 2021-09-23 | 8:50 | 17:30 | 8h | 0 | shanghai
Zhao Wenlong | CW39 | 2021-09-24 | 8:30 | 17:30 | 8h | 0 | shanghai
Zhao Wenlong | CW40 | 2021-09-26 | 8:40 | 17:30 | 8h | 0 | MA/ACB | 1、8K vehicle has been finish the FoV testing 100% 2、12K vehicle because the parking out function is not actived,so test case only has been finished 85%;
Zhao Wenlong | CW40 | 2021-09-27 | 8:50 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW40 | 2021-09-28 | 8:30 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW40 | 2021-09-29 | 8:45 | 18:00 | 8h | 0 | MA/ACB
Zhao Wenlong | CW40 | 2021-09-30 | 8:40 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW41 | 2021-10-08 | 8:30 | 17:30 | 8h | 0 | shanghai | 1、8K vehicle has been finish the FoV testing 100% 2、12K vehicle because the parking out function is not actived,so test case only has been finished 85%;
Zhao Wenlong | CW41 | 2021-10-09 | 8:45 | 18:00 | 8h | 0 | shanghai
Zhao Wenlong | CW42 | 2021-10-11 | 8:40 | 17:30 | 8h | 0 | shanghai | 1、12K parking test and finished 100%
Zhao Wenlong | CW42 | 2021-10-12 | 8:50 | 17:30 | 8h | 0 | shanghai
Zhao Wenlong | CW42 | 2021-10-13 | 8:30 | 17:30 | 8h | 0 | shanghai
Zhao Wenlong | CW42 | 2021-10-14 | 8:45 | 18:00 | 8h | 0 | shanghai
Zhao Wenlong | CW42 | 2021-10-15 | 8:40 | 17:30 | 8h | 0 | shanghai
Zhao Wenlong | CW43 | 2021-10-18 | 8:40 | 17:30 | 8h | 0 | MA/ACB | 1、A+SUVe parking test issues push and solve with Audi engineer ; 2、Cluster 3.3 parking test propration for C-BEV and A7L,the caar status correct with SW version and whether the function can be used.
Zhao Wenlong | CW43 | 2021-10-19 | 8:50 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW43 | 2021-10-20 | 8:30 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW43 | 2021-10-21 | 8:45 | 18:00 | 8h | 0 | MA/ACB
Zhao Wenlong | CW43 | 2021-10-22 | 8:40 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW44 | 2021-10-25 | 8:40 | 17:30 | 8h | 0 | MA/ACB | 1、A+SUVe parking test issues push and solve with Audi engineer ; 2、Cluster 3.3 parking test propration for C-BEV and A7L,the caar status correct with SW version and whether the function can be used.
Zhao Wenlong | CW44 | 2021-10-26 | 8:50 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW44 | 2021-10-27 | 8:30 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW44 | 2021-10-28 | 8:45 | 18:00 | 8h | 0 | MA/ACB
Zhao Wenlong | CW44 | 2021-10-29 | 8:40 | 17:30 | 8h | 0 | MA/ACB
Zhao Wenlong | CW45 | 2021-11-02 | 8:50 | 17:30 | 8h | 0 | shanghai | 1、A+SUVe parking issues cases retest and changed debug ECU 100%; 2、now there have only one issue to retest with debug ECU record XCP data,but debug ECU is bad by flashing software,so we only have finished work 10%; 3、that need to retest with new debug ECU next weeked ;
Zhao Wenlong | CW45 | 2021-11-03 | 8:30 | 17:30 | 8h | 0 | shanghai
Zhao Wenlong | CW45 | 2021-11-04 | 8:45 | 18:00 | 8h | 0 | shanghai
Zhao Wenlong | CW45 | 2021-11-05 | 8:40 | 17:30 | 8h | 0 | shanghai
Zhao Wenlong | CW45 | 2021-11-06 | 9:00 | 18:00 | 8h | 8h | shanghai
Zhao Wenlong | CW46 | 2021-11-08 | 8:50 | 17:30 | 8h | 0 | shanghai | 1、A+SUVe changed debug ECU and flashing SW 100%; 2、recoding XCP trace for issues cases 100% , XCP is very difficult to configure 3、parking test case finished 50% and will be finished all of the work in beijing .
Zhao Wenlong | CW46 | 2021-11-09 | 9:10 | 18:30 | 8h | 0 | shanghai
Zhao Wenlong | CW46 | 2021-11-10 | 8:30 | 17:30 | 8h | 0 | shanghai
Zhao Wenlong | CW46 | 2021-11-11 | 8:45 | 18:00 | 8h | 0 | shanghai
Zhao Wenlong | CW46 | 2021-11-12 | 9:45 | 18:00 | 8h | 0 | shanghai
Zhao Wenlong | CW46 | 2021-11-13 | 8:40 | 17:30 | 8h | 8h | shanghai
Zhao Wenlong | CW46 | 2021-11-14 | 9:00 | 18:00 | 8h | 8h | shanghai
Zhao Wenlong | CW47 | 2021-11-15 | 8:50 | 17:30 | 8h | 0 | shanghai | 1、borrow A+SUVe sportline vehicle from SVW EG and flashed DS of 0076&0044 re-test LP scenarioes ,that have the same problems of touch curb. 100%
Zhao Wenlong | CW47 | 2021-11-16 | 9:10 | 18:30 | 8h | 0 | shanghai
Zhao Wenlong | CW48 | 2021-11-24 | 9:10 | 14:30 | 4h | 0 | bejing | 1、return testig tools and transfer works of the parking test for Audi engineers
Hu Naitao | CW28 | 2021-07-05 | 9:00 | 17:30 | 8 | 0 | MA/ACB | 1、与奥迪工程师王帅对接。了解了MFK5的情况，已完成100%； 2、学习MFK5的12个感知模块的功能和数据采集路线的制定，已完成50%； 3、了解目前搭载MFK5的车型开发状态，已完成100%； 4、跟踪MFK5实际道路测试的设备集成和调试情况，已完成5%。
Hu Naitao | CW28 | 2021-07-06 | 9:00 | 17:30 | 8 | 0 | MA/ACB
Hu Naitao | CW28 | 2021-07-07 | 9:00 | 17:30 | 8 | 0 | MA/ACB
Hu Naitao | CW28 | 2021-07-08 | 9:00 | 17:30 | 8 | 0 | MA/ACB
Hu Naitao | CW28 | 2021-07-09 | 9:00 | 17:30 | 8 | 0 | MA/ACB
Hu Naitao | CW29 | 2021-07-12 | 9:00 | 17:30 | 8 | 0 | MA/ACB | 1、对MFK5的AHS/LDA/PED/MOD/PRE/TSR/HZD/ECR/WLA等功能模块的测试用例进行分类，已完成100%； 2、与德国那边交流，跟踪MFK5实际道路测试的设备集成和调试情况，已完成5%； 3、进行工作任务分工，负责编写和修改MOD&PED的test cases，已完成5%。
Hu Naitao | CW29 | 2021-07-13 | 9:00 | 17:30 | 8 | 0 | MA/ACB
Hu Naitao | CW29 | 2021-07-14 | 9:00 | 17:30 | 8 | 0 | MA/ACB
Hu Naitao | CW29 | 2021-07-15 | 9:00 | 17:30 | 8 | 0 | MA/ACB
Hu Naitao | CW29 | 2021-07-16 | 9:00 | 17:30 | 8 | 0 | MA/ACB
Hu Naitao | CW30 | 2021-07-19 | 9:00 | 17:30 | 8 | 0 | MA/ACB | 1、按照王帅提供的MFK5中国道路测试路线，编写和修改MOD&PED的test cases，删除一些不符合中国情况的TC，已完成40%； 2、与德国那边MFK5项目组开会，确认MFK5测试设备的状态，已完成100%； 3、和王鹏龙进行MFK5工作的讲解，已完成100%。
Hu Naitao | CW30 | 2021-07-20 | 9:00 | 17:30 | 8 | 0 | MA/ACB
Hu Naitao | CW30 | 2021-07-21 | 9:00 | 17:30 | 8 | 0 | MA/ACB
Hu Naitao | CW30 | 2021-07-22 | 9:00 | 17:30 | 8 | 0 | MA/ACB
Hu Naitao | CW30 | 2021-07-23 | 9:00 | 17:30 | 8 | 0 | MA/ACB
Hu Naitao | CW31 | 2021-07-26 | 9:00 | 17:30 | 8 | 0 | MA/ACB | 1、在天津开展A7L的ACC、aLDW、ACA、LIM功能的实际道路试验，每项功能测试里程150km； 2、掌握了测试设备的安装（ADAS功能FlexRay通信、仪表板监控摄像头、前向监控摄像头），CANape数据的采集和分析； 3、A7L的ADAS功能报错，无法继续试验，试验提前结束，周五返京。
Hu Naitao | CW31 | 2021-07-27 | 9:00 | 17:30 | 8 | 0 | MA/ACB
Hu Naitao | CW31 | 2021-07-28 | 9:00 | 17:30 | 8 | 0 | MA/ACB
Hu Naitao | CW31 | 2021-07-29 | 9:00 | 17:30 | 8 | 0 | MA/ACB
Hu Naitao | CW31 | 2021-07-30 | 9:00 | 17:30 | 8 | 0 | MA/ACB
Hu Naitao | CW32 | 2021-08-02 | 8:30 | 17:30 | 9 | 0 | MA/ACB | 1. I have written and modified test cases about MOD and PED modules of MFK5, and added 42 kinds of revelent test cases of EU-NCAP AEB_C2C and AEB_PED scenarios. 60% done; 2. The china parts of measurement equipments of MFK5 have been prepared to send to Germany on Augest 20. Q8 windshield that installed camera will be back to China before National Day. 20% done. 3. I have adjusted test route according to MOD and PED test cases to satisfy Chinese condition requests. 12 kinds of test cases are added. 60% done. 4. Based on the data of C-NCAP, I learn about data collection, data analysis by CANape software. 20% done. 5. Because of COVID-19 pandemic, traveling to Tianjin AVL is canceled.
Hu Naitao | CW32 | 2021-08-03 | 8:26 | 17:30 | 9.0667 | 0 | MA/ACB
Hu Naitao | CW32 | 2021-08-04 | 8:30 | 17:34 | 9.0667 | 0 | MA/ACB
Hu Naitao | CW32 | 2021-08-05 | 8:36 | 17:31 | 8.9167 | 0 | MA/ACB
Hu Naitao | CW32 | 2021-08-06 | 8:40 | 17:30 | 8.8333 | 0 | MA/ACB
Hu Naitao | CW33 | 2021-08-09 | 8:36 | 17:30 | 8.9 | 0 | MA/ACB | 1. I have written and modified test cases about MOD and PED modules of MFK5, and added the status of TCs to show if it can be available in China. Each TC was found multi chinese scenario photos to satisfy further road test. 65% done; 2. I have learned about project configuration data collection, data analysis of CANape software. 50% done; 3. I have test the questions of OPS and Rear View modules of A+SUVe, and collected data each condition. 100% done.
Hu Naitao | CW33 | 2021-08-10 | 8:40 | 17:30 | 8.8333 | 0 | MA/ACB
Hu Naitao | CW33 | 2021-08-11 | 8:30 | 17:30 | 9 | 0 | MA/ACB
Hu Naitao | CW33 | 2021-08-12 | 8:34 | 17:30 | 8.9333 | 0 | MA/ACB
Hu Naitao | CW33 | 2021-08-13 | 8:20 | 17:30 | 9.1667 | 0 | MA/ACB
Hu Naitao | CW34 | 2021-08-16 | 8:30 | 17:30 | 9 | 0 | MA/ACB | 1. According to the requirement of Audi Germany, two states of the test cases, Add in China and Modify in China, are retained. And TCs which can be tested in Germany are deleted. 70% done; 2. Applying for installing the test software with audi's PC and setting up the Germany VPN; 3. Traveling to Tianjin to test the VZE function of A7L, including SL, cancellation of SL, no-overtaking and cancellation of no-overtaking. there are 12 test problems found. 100% done.
Hu Naitao | CW34 | 2021-08-17 | 8:30 | 17:30 | 9 | 0 | MA/ACB
Hu Naitao | CW34 | 2021-08-18 | 8:23 | 17:34 | 9.1833 | 0 | MA/ACB
Hu Naitao | CW34 | 2021-08-19 | 8:20 | 18:00 | 9.6667 | 0 | MA/ACB
Hu Naitao | CW34 | 2021-08-20 | 8:00 | 19:00 | 11 | 0 | Tianjin
Hu Naitao | CW34 | 2021-08-21 | 7:00 | 11:00 | 4 | 4 | TJ to BJ
Hu Naitao | CW35 | 2021-08-23 | 8:36 | 17:30 | 8.9 | 0 | MA/ACB | 1. According to the requirement of Audi Germany, two states of the test cases, Add in China and Modify in China, are retained. And TCs which can be tested in Germany are deleted. 100% done; 2. TCs are added chinese relevent ADAD/AD standards and protocols. 32 kinds of TCs from C-NCAP/C-IASI/CCRT/GBT are being written. 30% done; 3. send test equipments of MFK5 with Wang Shuai to Germany to install the rest of hardware and debug them. 100% done.
Hu Naitao | CW35 | 2021-08-24 | 8:40 | 17:30 | 8.8333 | 0 | MA/ACB
Hu Naitao | CW35 | 2021-08-25 | 8:30 | 17:30 | 9 | 0 | MA/ACB
Hu Naitao | CW35 | 2021-08-26 | 8:34 | 17:30 | 8.9333 | 0 | MA/ACB
Hu Naitao | CW35 | 2021-08-27 | 8:20 | 17:30 | 9.1667 | 0 | MA/ACB
Hu Naitao | CW36 | 2021-08-30 | 8:37 | 17:37 | 8h | 0 | MA/ACB | 1. TCs are added chinese relevent ADAD/AD standards and protocols. 60 kinds of TCs from C-NCAP/C-IASI/CCRT/GBT are being written. 60% done. 2. Have the meeting with Audi Germany, and review the test cases of MOD&PED. 100% done. 3. Go through the formalities of deliverying MFK5 test equipments. 100% done.
Hu Naitao | CW36 | 2021-08-31 | 8:30 | 17:30 | 8h | 0 | MA/ACB
Hu Naitao | CW36 | 2021-09-01 | 8:30 | 17:40 | 8h | 0 | MA/ACB
Hu Naitao | CW36 | 2021-09-02 | 8:36 | 17:34 | 8h | 0 | MA/ACB
Hu Naitao | CW36 | 2021-09-03 | 8:40 | 17:34 | 8h | 0 | MA/ACB
Hu Naitao | CW37 | 2021-09-06 | 8:36 | 17:30 | 8h | 0 | MA/ACB | 1. TCs are added chinese relevent ADAD/AD standards and protocols. 108 kinds of TCs from C-NCAP/C-IASI/GBT are being written. 100% done; 2. Testing A+SUV IPA functions. And deploying CANape data collection project. The car was sent to Shanghai. 100% done.
Hu Naitao | CW37 | 2021-09-07 | 8:40 | 17:30 | 8h | 0 | MA/ACB
Hu Naitao | CW37 | 2021-09-08 | 8:30 | 17:30 | 8h | 0 | MA/ACB
Hu Naitao | CW37 | 2021-09-09 | 8:34 | 17:30 | 8h | 0 | MA/ACB
Hu Naitao | CW37 | 2021-09-10 | 8:20 | 17:30 | 8h | 0 | MA/ACB
Hu Naitao | CW38 | 2021-09-13 | 8:30 | 17:30 | 8h | 0 | MA/ACB | 1. modify TCs of MOD & PED and add the year and title of standard and protocol. 100% done; 2. Testing the rear view and top view of Audi A3 from FVW. 100% done; 3. discussing the next working plan of MFK5 with Wang Shuai. Adding the relevent signals of test cases. 5% done.
Hu Naitao | CW38 | 2021-09-14 | 8:30 | 17:30 | 8h | 0 | MA/ACB
Hu Naitao | CW38 | 2021-09-15 | 8:23 | 17:34 | 8h | 0 | MA/ACB
Hu Naitao | CW38 | 2021-09-16 | 8:20 | 18:00 | 8h | 0 | MA/ACB
Hu Naitao | CW38 | 2021-09-17 | 8:32 | 17:40 | 8h | 0 | MA/ACB
Hu Naitao | CW38 | 2021-09-18 | 8:40 | 18:00 | 9.3333 | 0 | MA/ACB
Hu Naitao | CW39 | 2021-09-22 | 8:36 | 17:30 | 8h | 0 | MA/ACB | 1. Modify TCs of MOD & PED and add relevant signals in expected results to make sure the accuracy of test. 10% done; 2. Write the A3 TV and RV test report, and discuss with audi engineers about the test problem. 100%done; 3. prepare the ASUVe test vehicles, and be ready to test TV and RV next week. 10%done.
Hu Naitao | CW39 | 2021-09-23 | 8:40 | 17:30 | 8h | 0 | MA/ACB
Hu Naitao | CW39 | 2021-09-24 | 8:20 | 18:00 | 8h | 0 | MA/ACB
Hu Naitao | CW40 | 2021-09-26 | 8:36 | 17:36 | 8h | 0 | MA/ACB | 1. Modify TCs of MOD & PED and add relevant signals in expected results to make sure the accuracy of test. 30% done; 2. Prepare the ASUVe test vehicles, and test TV and RV static and dynamic test catalogs. 50%done.
Hu Naitao | CW40 | 2021-09-27 | 8:30 | 17:42 | 8h | 0 | MA/ACB
Hu Naitao | CW40 | 2021-09-28 | 8:26 | 17:30 | 8h | 0 | MA/ACB
Hu Naitao | CW40 | 2021-09-29 | 8:34 | 17:36 | 8h | 0 | MA/ACB
Hu Naitao | CW40 | 2021-09-30 | 8:20 | 17:20 | 8h | 0 | MA/ACB
Hu Naitao | CW41 | 2021-10-08 | 10:30 | 20:41 | 9 | 1 | CICV | 1. Modify TCs of MOD & PED and add relevant signals in expected results to make sure the accuracy of test. TCs will be checked with Audi colleagues next Monday. 100% done; 2. Test ASUVe RV dynamic test cases and collect relevant test data . 100%done.
Hu Naitao | CW41 | 2021-10-09 | 9:28 | 19:54 | 8 | 0 | CICV
Hu Naitao | CW42 | 2021-10-11 | 9:04 | 18:09 | 8 | 0 | CICV | 1. According to the meeting request, modify and review TCs in codebeamer system with the function defination. Now I am waiting for codebeamer template. 5% done; 2. Test ASUVe TV static and dynamic test cases and collect relevant test data. 100%done; 3. review ASUVe RV static test cases, and write RV and TV test reports. 50% done.
Hu Naitao | CW42 | 2021-10-12 | 8:16 | 18:32 | 9 | 1 | CICV
Hu Naitao | CW42 | 2021-10-13 | 9:17 | 18:28 | 8 | 0 | CICV
Hu Naitao | CW42 | 2021-10-14 | 9:16 | 19:27 | 9 | 1 | CICV
Hu Naitao | CW42 | 2021-10-15 | 9:20 | 18:25 | 8 | 0 | CICV
Hu Naitao | CW43 | 2021-10-18 | 9:18 | 19:21 | 9 | 1 | CICV | 1. According to the meeting request, modify and review TCs in codebeamer system with the function defination. Now test case codebeamer template has been reviewed by MFK5 project meeting. I will start to write TCs in system. 10% done; 2. Ensure the state of MFK5 test equipments with Wang Jian. 100% done; 3. Prepare A+SUVe Delta ME3 rear view test vehicle, and write ASUVe TV test report. 100%done.
Hu Naitao | CW43 | 2021-10-19 | 9:12 | 18:25 | 8 | 0 | CICV
Hu Naitao | CW43 | 2021-10-20 | 9:26 | 19:30 | 9 | 1 | CICV
Hu Naitao | CW43 | 2021-10-21 | 9:15 | 18:26 | 8 | 0 | CICV
Hu Naitao | CW43 | 2021-10-22 | 8:30 | 17:36 | 8 | 0 | CICV
Hu Naitao | CW44 | 2021-10-25 | 9:01 | 19:18 | 9 | 1 | CICV | 1. Review the test cases of MOD with MFK5 project managers, 16 keys modification must be finished before next Monday regular meeting with Germany. 90%done; 2. Write the TCs in Codebeamer, including the usual TCs and Chinese special conditions. 15%done. 3. Travel to Changchun to assist Rongting to verify the top view and rear view functions testing ability of FAW-VW. Two vehicles must be finished. 80%done.
Hu Naitao | CW44 | 2021-10-26 | 8:46 | 18:57 | 9 | 1 | CICV
Hu Naitao | CW44 | 2021-10-27 | 11:30 | 18:51 | 6 | -2 | CICV
Hu Naitao | CW44 | 2021-10-28 | 8:55 | 19:00 | 9 | 1 | CICV
Hu Naitao | CW44 | 2021-10-29 | 8:08 | 18:10 | 9 | 1 | CICV
Hu Naitao | CW45 | 2021-11-01 | 8:00 | 19:00 | 8 | 0 | FAW-VW | 1. Review the test cases of MOD with MFK5 project managers, 16 keys modification must be finished before next Monday regular meeting with Germany. 100%done; 2. Write the TCs in Codebeamer, including the usual TCs and Chinese special conditions. 30%done. 3. Travel to Changchun to assist Rongting to verify the top view and rear view functions testing ability of FAW-VW. Two vehicles must be finished. 100%done.
Hu Naitao | CW45 | 2021-11-02 | 8:00 | 19:00 | 8 | 0 | FAW-VW
Hu Naitao | CW45 | 2021-11-03 | 8:11 | 17:56 | 8 | 0 | FAW-VW
Hu Naitao | CW45 | 2021-11-04 | 8:40 | 17:50 | 8 | 0 | MA/ACB
Hu Naitao | CW45 | 2021-11-05 | 8:36 | 17:34 | 8 | 0 | MA/ACB
Hu Naitao | CW46 | 2021-11-08 | 8:20 | 17:48 | 8 | 0 | MA/ACB | 1. Write the TCs in Codebeamer, including the usual TCs and Chinese special conditions. 40%done. 2. Carry on the ASUVe ME3 Delta rearview and topview function and write test report. 50%done.
Hu Naitao | CW46 | 2021-11-09 | 8:31 | 17:35 | 8 | 0 | MA/ACB
Hu Naitao | CW46 | 2021-11-10 | 8:36 | 17:30 | 8 | 0 | MA/ACB
Hu Naitao | CW46 | 2021-11-11 | 8:34 | 17:36 | 8 | 0 | MA/ACB
Hu Naitao | CW46 | 2021-11-12 | 8:20 | 17:46 | 8 | 0 | MA/ACB
Hu Naitao | CW47 | 2021-11-15 | 8:26 | 18:00 | 8 | 0 | MA/ACB | 1. Write the TCs in Codebeamer, including the usual TCs and Chinese special conditions. 50%done. 2. Carry on the ASUVe ME3 Delta rearview and topview function and write test report. 100%done.
Hu Naitao | CW47 | 2021-11-16 | 8:36 | 17:30 | 8 | 0 | MA/ACB
Hu Naitao | CW47 | 2021-11-17 | 8:40 | 20:10 | 8 | 0 | beijing
Hu Naitao | CW47 | 2021-11-18 | 8:43 | 17:30 | 8 | 0 | beijing
Hu Naitao | CW47 | 2021-11-19 | 8:43 | 17:30 | 8 | 0 | beijing
Hu Naitao | CW48 | 2021-11-22 | 8:43 | 17:54 | 8 | 0 | beijing | 1. Write the TCs in Codebeamer, including the usual TCs and Chinese special conditions. 80%done. 2. Hand over MOD and PED test cases work. 100%done.
Hu Naitao | CW48 | 2021-11-23 | 8:34 | 18:30 | 8 | 0 | beijing
Hu Naitao | CW48 | 2021-11-24 | 8:30 | 18:56 | 8 | 0 | beijing
Yang Xueying | CW36 | 2021-08-30 | 8:53 | 19:01 | 10h | 1 | Working from home | 1. Between Monday and Wednesday noon, both LDA and TSR Test Cases are rewritten or improved based on the existing (self-found) Standard, Regulation and Laws. This means that for TSR functions, the dimensions, the different speed limits for different situations in Description, Precondition, Action, Expected Result and Comment were added and then improved. 2. On Wednesday a conference with Johannes (Audi AG), Shuai and Naitao was held. First, Shuai had presented his work with Johannes last week. The facility was accepted by DHL on Thursday last week. The progress of the data solution was then submitted. Shuai also said that the export of all relevant files and included in the shared folder. The activation of the access to the Sharefolder for Xueying and Naitao is unfortunately not yet successful. The delivery of Windschield will be done in CW37 (Bosch CW36). The very short (1-2 min) presentation about TSR test cases from Xueying to others. Because Johnannes had to attend another conference. Unfortunately, Xueying did not have time to ask her questions. After the conference, Shuai let Xueying and Naitao continue to write the test cases according to the standards, laws and regulations of China first. After receiving the Euro standard files, the written test cases must be reviewed, the difference between China and Europe must be noted in the test cases. 3. Between Wednesday and Friday continued to rewrite, review and improve. Plan to work on Sunday.
Yang Xueying | CW36 | 2021-08-31 | 8:58 | 19:29 | 10h | 1 | Working from CICV
Yang Xueying | CW36 | 2021-09-01 | 9:03 | 19:08 | 9h | 1 | Working from CICV
Yang Xueying | CW36 | 2021-09-02 | 8:36 | 17:40 | 8h | 0 | Working from CICV
Yang Xueying | CW36 | 2021-09-03 | 8:30 | 19:00 | 10h | 1 | Working from CICV
Yang Xueying | CW37 | 2021-09-06 | 8:33 | 19:00 | 9h | 1 | off-site | 1. Between Monday and Wednesday afternoon the new test cases from both LDA & TSR with test standard were added, present test cases were also improved. (Johannes was on vacation on Monday, so the conference with Audi AG this week was canceled) 2. A meeting between Shuai and Naitao was held on Wednesday afternoon. The contents of the meeting are as follows： a. @Shuai's work: the files are prepared for customs clearance. Naitao and Xueying have no access to shared folder yet. b. Shuai wanted to receive the Excel files made up of MOD, PED, LDA and TSR test cases on friday and to hand them over to Audi AG the next Monday. Unfortunately, Xueying needs more time due to changing demands and size of work. Xueying had shown the rest of her work and asked for at least two more weeks, and Shuai replied that the submission can be delayed by 2 days. c. After discussion, the road test of the test cases, which take into account the standard safety function, can be carried out in the test station. 3. The following work was done between Wednesday 4 p.m. and Friday 5 p.m. a. The content of the content and requirements from Shuai are sorted, the solution of the requirement is found and planed. b. the test cases are according to different scenarios in City Road, Country Road, Mountain Road, Highway and test station filterd, and some photoes und cases which are no longer needed, are deleted. c. about 55 test cases are improved and 45 incomplete cases are fillded. 13 test case for test station with standard (GB, C-NCAP) are added. 4. the work on CW 37 are as follows： a. TSR Traffic Light Test Cases to write b. Test Cases for Test station to write c. improve present wrote test cases d. excel file format to adjustment
Yang Xueying | CW37 | 2021-09-07 | 9:09 | 18:40 | 8h | 0 | off-site
Yang Xueying | CW37 | 2021-09-08 | 7:30 | 18:01 | 9h | 1 | off-site
Yang Xueying | CW37 | 2021-09-09 | 7:58 | 17:03 | 8h | 0 | off-site
Yang Xueying | CW37 | 2021-09-10 | 7:47 | 17:00 | 8h | 0 | off-site
Yang Xueying | CW38 | 2021-09-13 | 8:09 | 17:10 | 8h | 0 | off-site | 1. Regular meeting with MA on Wednesday afternoon (13:30-14:30, 16:00-17:00): a. MFK5 China Specific Usecases (images), Signal list of LDA, TSR, MOD, PED were input to Naitao and Xueying b. the images of real scenario of LDA/TSR/MOD/PED shall be added c. the signal of LDA/TSR/MOD/PED shall be according to the signal list added. d. each test case must include all signal that the cameras perceive. e. the dimension (e.g., length and gap of dash, width of line and dimension of traffic sign) shall be no more in Expected Result considered. f. Korea and Japan specific cases will be later considered. If it is no Corona in next year, the road test will be in Korea and Japan carried out. 2. Regular meeting with Audi AG on Thursday afternoon: a. test Software: ADTFS MCCS shall be installed. Shuai has no Access to the MFK5 (DE) Shared Folder yet. Johannes said, it takes usually long. b. test Cases: aignal shall be according to the given signal list in shared folder in China use cases added. The lateral lines shall be not as LDA considered. c. KT: PO signature from CFO will be in CW 38.7 done. d. data sample: EMapgo can transfer raw data to Magna-Kotei Datacenter. e. windshield: Windshields are available in CW 38.5. Camera on Windshields is a big problem. f. CodeBeamer: Code beamer shall be used. 3. Work content this week: the test routes (Shanghai and Chongqing) were improved, reviewed the test cases with TSR-Photos from Germany, Germany test cases, signal list (double check) and add the signals. 4. Work next week: reviewed the test cases with TSR-Photos from Germany, Germany test cases, signal list (double check) and add the signals and review the LDA test case with signal list and add the corresponding signals.
Yang Xueying | CW38 | 2021-09-14 | 9:04 | 18:35 | 8h | 0 | off-site
Yang Xueying | CW38 | 2021-09-15 | 8:06 | 17:30 | 8h | 0 | off-site
Yang Xueying | CW38 | 2021-09-16 | 8:08 | 17:15 | 8h | 0 | off-site
Yang Xueying | CW38 | 2021-09-17 | 8:25 | 17:30 | 8h | 0 | off-site
Yang Xueying | CW38 | 2021-09-18 | 9:00 | 18:00 | 8h | 0 | off-site
Yang Xueying | CW39 | 2021-09-20 | 12:30 | 14:30 | 2h | 2 | off-site | 1. Regular meeting with MA on Wednesday afternoon (13:30-14:30, 16:00-17:00): a. MFK5 China Specific Usecases (images), Signal list of LDA, TSR, MOD, PED were input to Naitao and Xueying b. the images of real scenario of LDA/TSR/MOD/PED shall be added c. the signal of LDA/TSR/MOD/PED shall be according to the signal list added. d. each test case must include all signal that the cameras perceive. e. the dimension (e.g., length and gap of dash, width of line and dimension of traffic sign) shall be no more in Expected Result considered. f. Korea and Japan specific cases will be later considered. If it is no Corona in next year, the road test will be in Korea and Japan carried out. 2. Regular meeting with Audi AG on Thursday afternoon: a. test Software: ADTFS MCCS shall be installed. Shuai has no Access to the MFK5 (DE) Shared Folder yet. Johannes said, it takes usually long. b. test Cases: aignal shall be according to the given signal list in shared folder in China use cases added. The lateral lines shall be not as LDA considered. c. KT: PO signature from CFO will be in CW 38.7 done. d. data sample: EMapgo can transfer raw data to Magna-Kotei Datacenter. e. windshield: Windshields are available in CW 38.5. Camera on Windshields is a big problem. f. CodeBeamer: Code beamer shall be used. 3. Work content this week: the test routes (Shanghai and Chongqing) were improved, reviewed the test cases with TSR-Photos from Germany, Germany test cases, signal list (double check) and add the signals. 4. Work next week: reviewed the test cases with TSR-Photos from Germany, Germany test cases, signal list (double check) and add the signals and review the LDA test case with signal list and add the corresponding signals.
Yang Xueying | CW39 | 2021-09-22 | 7:24 | 19:34 | 11h | 3 | off-site
Yang Xueying | CW39 | 2021-09-23 | 8:58 | 18:10 | 8h | 0 | off-site
Yang Xueying | CW39 | 2021-09-24 | 8:05 | 17:38 | 8h | 0 | off-site
Yang Xueying | CW39 | 2021-09-25 | 8:33 | 17:40 | 8h | 8 | off-site
Yang Xueying | CW40 | 2021-09-26 | 8:58 | 21:00 | 11h | 3 | off-site | 1. Regular meeting with Audi AG on Monday afternoon (14:30-15:00): a. KT: PO signature from CFO is done. b. Data Solution: Magna license holder. (Due to bad internet connection, more info is not clear) c. NDA: three party (NDA between Mobileye/MA/BOSCH). (Due to bad internet connection, more info is not available) d. ADTF MCCS, Purchase Order for 2022, Prelabel-Tools and windshield: (Due to bad internet connection, more info is not available) e. 3C-Certificate of Windshields shall be carried out by Shuai. f. Windshield: Windshields are available in CW 38.5. Camera on Windshields is a big problem. g. Test Software: ADTFS MCCS shall be installed. Shuai has no Access to the MFK5 (DE) Shared Folder yet. Johannes said, it takes usually long. h. Test Cases: Signal shall be according to the given signal list in shared folder in China use cases added. The lateral lines shall be not as LDA considered. i. CodeBeamer: Code beamer shall be used. 2. Regular meeting with MA on Wednesday afternoon (15:15-15:40): a. LAH of LDA/TSR/MOD/PED were on last Sunday 17 Uhr in Shared Folder input. Shuai said, that he has forgot to tell to Xueying and the target is, basis of the LAH to write the China specific test cases. b. the images of real scenario of LDA/TSR/MOD/PED shall be added c. the signal of LDA/TSR/MOD/PED shall be according to the signal list added. d. each test case must include all signal that the cameras perceive. e. the dimension (e.g., length and gap of dash, width of line and dimension of traffic sign) shall be no more in Expected Result considered. f. Xueying said that in Germany cases the lateral lines are considered as LDA too. Shuai lets Xueying lateral lines in both LDA and TSR to write as previously. g. an about 1054.8 km long test route from Tianjin via Shijiazhuang and Zhangjiakou to Tianjin is planed by Shuai. Shuai and a colleague from VW Group will drive the test car, Naitao and Xueying will record review data during the test, record the issue/special case with description. No data will be recorded during the test because no license yet. Test route for perception module need to be separated (will be late done by Naitao) 3. Work content this week: reviewed the test cases with TSR-Photos from Germany, Germany test cases, signal list (double check) and add the signals. 4. Work next week: basis of Lastenheft to review the test cases with TSR-Photos from Germany, Germany test cases, signal list (double check) and add the signals and review the LDA test case with signal list and add the corresponding signals and learn how to use Codebeamer.
Yang Xueying | CW40 | 2021-09-27 | 9:28 | 18:30 | 8h | 0 | off-site
Yang Xueying | CW40 | 2021-09-28 | 8:53 | 18:00 | 8h | 0 | off-site
Yang Xueying | CW40 | 2021-09-29 | 8:33 | 18:36 | 9h | 1 | off-site
Yang Xueying | CW40 | 2021-09-30 | 9:00 | 18:00 | 8h | 0 | off-site
Yang Xueying | CW41 | 2021-10-08 | 10:30 | 20:41 | 9 | 1 | CICV | 1. Regular meeting with Audi AG on Monday: Data sample introduction with EMapGo 2. test cases shall be improved according to LAH and written in Codebeamer (5%)
Yang Xueying | CW41 | 2021-10-09 | 9:28 | 19:54 | 8 | 0 | CICV
Yang Xueying | CW42 | 2021-10-11 | 9:04 | 18:09 | 8 | 0 | CICV | 1. Regular meeting with MA: a. the eqiument will be arrived in end Sept. and the road test will be started in December b. testing plan and route was shared by Shuai and shall be checked with Johannes 2. test cases shall be improved according to LAH and written in Codebeamer (10%）
Yang Xueying | CW42 | 2021-10-12 | 8:16 | 18:32 | 9 | 1 | CICV
Yang Xueying | CW42 | 2021-10-13 | 9:17 | 18:28 | 8 | 0 | CICV
Yang Xueying | CW42 | 2021-10-14 | 9:16 | 19:27 | 9 | 1 | CICV
Yang Xueying | CW42 | 2021-10-15 | 9:20 | 18:25 | 8 | 0 | CICV
Yang Xueying | CW43 | 2021-10-18 | 9:18 | 19:21 | 9 | 1 | CICV | 1. Regular meeting with Audi AG on Monday: NDA between RB, MA and Magna shall be done; Data exchange between Kotei and EMapGo is still in Discussion; Purchase Order 2022 is still in discussion; all signature for KT PO were done. Delivery date for NI device will be on end Nov.; Windshields were sent to Johannes but not delivered. 2. Regular meeting with MA: a. introduce the staus to new college Fumin (MFK5 Testing Manager) b. Exchange codebeamer with Zhipeng 3. Codebeamer exchange with Jiaxi 4. test cases shall be improved according to LAH and written in Codebeamer (10%）
Yang Xueying | CW43 | 2021-10-19 | 9:12 | 18:25 | 8 | 0 | CICV
Yang Xueying | CW43 | 2021-10-20 | 9:26 | 19:30 | 9 | 1 | CICV
Yang Xueying | CW43 | 2021-10-21 | 9:15 | 18:26 | 8 | 0 | CICV
Yang Xueying | CW43 | 2021-10-22 | 8:30 | 17:36 | 8 | 0 | CICV
Yang Xueying | CW44 | 2021-10-25 | 9:01 | 19:18 | 9 | 1 | CICV | 1. Regular meeting with Audi AG: Jian was introduced as successor of Hengfeng to Johannes; the statement which provided by EMG was shared to Johannes; Purchase order 2021 in discussion; windshields+2c sample MFK5 were sent by Johannes and not delivered to MA; Test cases review termin next week 2. review with MA on Tuesday (MOD & PED: about 80% done, TSR & LDA: 0%) 3. test cases shall be improved according to LAH and written in Codebeamer (15%）
Yang Xueying | CW44 | 2021-10-26 | 8:46 | 18:57 | 9 | 1 | CICV
Yang Xueying | CW44 | 2021-10-27 | 11:30 | 18:51 | 6 | -2 | CICV
Yang Xueying | CW44 | 2021-10-28 | 8:55 | 19:00 | 9 | 1 | CICV
Yang Xueying | CW44 | 2021-10-29 | 8:08 | 18:10 | 9 | 1 | CICV
Yang Xueying | CW45 | 2021-11-01 | 8:58 | 18:23 | 8 | 0 | CICV | 1. Regular meeting with Audi AG on Friday: 2. Regular meeting with MA on Wednesday: about 100 TCs were by MA reviewed. 2. test cases shall be improved according to LAH and written in Codebeamer (20%)
Yang Xueying | CW45 | 2021-11-02 | 9:09 | 18:23 | 8 | 0 | CICV
Yang Xueying | CW45 | 2021-11-03 | 9:25 | 18:39 | 8 | 0 | CICV
Yang Xueying | CW45 | 2021-11-04 | 9:28 | 18:52 | 8 | 0 | CICV
Yang Xueying | CW45 | 2021-11-05 | 9:27 | 18:30 | 8 | 0 | CICV
Yang Xueying | CW46 | 2021-11-08 | 9:12 | 18:46 | 8 | 0 | CICV | 1. Regular meeting with Audi AG on Monday: Johannes will leave in December 2. Regular meeting with MA on Wednesday: about 100 TCs were by MA reviewed. 2. test cases shall be improved according to LAH and written in Codebeamer (25%)
Yang Xueying | CW46 | 2021-11-09 | 9:23 | 18:45 | 8 | 0 | CICV
Yang Xueying | CW46 | 2021-11-10 | 9:04 | 18:23 | 8 | 0 | CICV
Yang Xueying | CW46 | 2021-11-11 | 9:20 | 18:52 | 8 | 0 | CICV
Yang Xueying | CW46 | 2021-11-12 | 9:18 | 18:25 | 8 | 0 | CICV
Yang Xueying | CW47 | 2021-11-15 | 9:17 | 19:07 | 8 | 0 | CICV | 1. Regulation Meeting with Audi AG on Monday: no Information related to our cases work 2. Review with MA: about 50 cases were reviewed 3. Review with DE: new requirements were given by Fabian Stark. The Confidence and Position shall be added for every cases. Other Cases shall be as quickly as possible added 4. test cases shall be improved according to LAH and written in Codebeamer (35%)
Yang Xueying | CW47 | 2021-11-16 | 9:16 | 18:35 | 8 | 0 | CICV
Yang Xueying | CW47 | 2021-11-17 | 9:17 | 18:25 | 8 | 0 | CICV
Yang Xueying | CW47 | 2021-11-18 | 9:15 | 18:35 | 8 | 0 | CICV
Yang Xueying | CW47 | 2021-11-19 | 9:02 | 18:10 | 8 | 0 | CICV
Yang Xueying | CW48 | 2021-11-22 | 9:17 | 19:07 | 8 | 0 | CICV | 1. Regulation Meeting with Audi AG on Monday: no Information related to our cases work 2. Hand over the work 3. Test cases shall be improved according to LAH and written in Codebeamer (45%)
Yang Xueying | CW48 | 2021-11-23 | 9:16 | 18:35 | 8 | 0 | CICV
Yang Xueying | CW48 | 2021-11-24 | 9:17 | 18:25 | 8 | 0 | CICV